## Tracker
Item | What it is / why it matters | Build guidance | Status | Notes
PRIORITY QUEUE — LOCKED BY ADAM SEP 21 (work in this order) · 4 items
1. Business application Typeform rebuild — awaiting team question verdict | Sep 21: the application form is being rebuilt as a Typeform-style flow. Believed broken since launch; the money+membership path gets maximum rigor. | Blocked on the team's verdict on the application QUESTIONS (what we ask, in what order, what routes to membership vs Preferred Business vs sponsorship). Then: form -> review/approval -> payment -> provisioning -> comms, recon-first, keystroke-standard develop rehearsal both viewports, ship. Adam walkthrough Q&A at build start (approval mechanics, reviewer, pricing incl. annual, notification emails). | WAITING ON ADAM: team question verdict | PRIORITY 1. Absorbs the old "Business application process: fix, test, launch" sprint row and the empty "Verify the business application approval works" row. Pairs with "/business page rebuild with dynamic application".
2. Hub pages build (external hub pages) — walkthrough next; pre-gate CLEARED Sep 21 | Four audience-specific public landers (cltarrival / cltfounded / clteatsandevents / cltreset) that funnel Charlotte audiences into the club. These are the first outside-facing surfaces reading hub data, so the RLS audit was the mandatory pre-gate. | 4 public landers, shared skeleton, own design pass, fully pre-rendered + schema (see SEO item). They feed The Network. Pre-gate: cursor_report_rlsaudit.md — none of the 17 RLS-on/no-policy tables is a hub, task or member-surface table; leftover anon/authenticated grants stripped on prod (by hand) and develop (migration 20260921070000). Next step is Adam's walkthrough of the page set, then build. | Build — walkthrough next | PRIORITY 2. Pre-gate CLEARED Sep 21. Was "Charlotte hub landing sites (4 public landers)". Pairs with "The Network" (internal roll-up) and the SEO/pre-render row. Social members never appear on the public hubs.
3. Task management system — walkthrough | A super-light ClickUp-style task center for admins/super-admins: create, assign, track tasks. Sep 21: promoted from Phase 2 into the locked queue. | Adam walkthrough of the task model (create / assign / track, who sees what, notifications via the existing bell) then own detailed scope, then build. Reuse the existing tasks tables and task_assigned bell type where they fit. | Build — walkthrough | PRIORITY 3. Was "Task center for admins (lite project tool)" under Phase 2 major builds. Note the existing "Speed up slow list pages (Events, Tasks, Hubs)" row touches the same tables.
4. Mobile app — Apple transfer DONE; email sync + tickets waves ride before it | A full native mobile application. The largest Phase 2 build. Sep 21: Apple developer account transfer is DONE. Two identity waves ride before the app so it is built on a settled identity model. | Sequence: identity Wave 7 (email change keeps Stripe in sync) and Wave 9 (retire legacy tickets / capacity split-brain) first, then own detailed scope for the app, then build. Do not start the app on the dual-write ticket tables. | Build — after Waves 7 + 9 | PRIORITY 4. Was "Full mobile app" under Phase 2 major builds. Apple transfer done. The two prerequisite waves keep their own rows (MEMBERS & MONEY / IDENTITY FOUNDATION).
SEP 21 ADDITIONS — POST-IDENTITY-PACKAGE FOLLOW-UPS · 10 items
Meta CAPI — server-side Purchase events (dedupe with the browser pixel by event_id) | The Meta pixel (d31dba9) fires Purchase client-side with eventID = the checkout session id, deduped per session. Browser-only events are lost to ad blockers and in-app browsers (the Nyree case) — CAPI sends the same Purchase server-side from the webhook so Meta sees every paid conversion once. | From stripe-webhook checkout.session.completed (or the verify-checkout path): POST to the Conversions API with event_name Purchase, event_id = cs_ id (matches the pixel), value/currency, hashed email, fbclid/fbc from the session metadata already stamped by create-checkout. Env-gated like the pixel. Rehearse with Meta test_event_code on develop; no real Meta calls otherwise. | Build | Depends on the Meta BM restructure + domain verification row (CAPI needs a verified domain and a system-user token). Pixel + UTM capture shipped Sep 15.
Meta Business Manager restructure + domain verification | The ad account / pixel / page live in a Business Manager structure that needs restructuring, and 704collective.com is not domain-verified in Meta. Domain verification is required for aggregated event measurement and CAPI. | Adam (Meta side): restructure BM ownership, verify 704collective.com (meta-tag or DNS TXT), attach the pixel to the verified domain, create a system user + CAPI token. Repo side if needed: one meta-tag in the root layout for verification. | ADAM — Meta side | Prerequisite for the CAPI row. Owner task; repo change is at most one meta tag.
Identity Wave 6E — drop the legacy contacts columns after soak (PARKED) | Waves 6A–6D-a are live: contacts link to people at write time (6C triggers), tags mirror to person_tags, opt-out truth is people.marketing_unsubscribed, email readers flipped. The legacy columns (contacts.unsubscribed, contact_tags as a read surface, profiles.marketing_unsubscribed for two profile-side readers) are still written for compatibility. 6E removes them. | After a soak and after 6D-b (admin surfaces) flips the last readers: drop/retire the legacy opt-out columns and contact_tags reads, repoint event-reminder and discussion-open off profiles.marketing_unsubscribed, remove the mirror lines from the 6C triggers. Migration + small code; rehearse on develop. | PARKED | Deliberately parked: nothing is wrong today because 6C keeps every legacy column current. Sequenced after 6D-b.
Identity Wave 6D-b — admin CRM/contacts surfaces read person-side truth (rides the admin rebuild) | The admin contacts/CRM pages, the attendee dialog and comp-invite still read contacts / contact_tags / legacy opt-out columns (cursor_report_wave6d.md §2). Correct today because 6C mirrors, but they are the last readers keeping the legacy shape alive. | Flip the admin readers to people / person_tags / people.marketing_unsubscribed. Needs grant select on person_tags to authenticated + an admin-only select policy (person_tags is service-role only today). Ride with "Build the admin area into clean sections" so each page is touched once. | QUEUED — rides admin rebuild | Deferred by design in the 6D recon. Unblocks 6E.
Identity Wave 8 — auth cutover (PARKED) | The final identity wave: auth-adjacent writes (signup, email change, password flows) key entirely on the person record with profiles as a settings/billing satellite. Wave A already mints a person at signup; 6C links every contact write; the cutover is the remaining piece. | Own scope before build. Regression-test logins + RLS from a non-admin session behind a verified backup/rollback, as the identity plan always required. Sequence after Wave 7 (email sync). | PARKED | Parked until Waves 7 and 9 land and the mobile app scope is known — the app is the consumer that decides how much cutover is needed.
Expiring-card Stripe toggle — Adam, 5 seconds | Stripe can email customers automatically when a saved card is about to expire (Billing -> Subscriptions and emails -> "Send emails about expiring cards"). It is off. Turning it on removes a class of avoidable past_due. | Adam: Stripe dashboard -> Settings -> Billing -> Subscriptions and emails -> enable expiring-card emails. Confirm the sender/branding matches the receipts. No code. | ADAM — 5 seconds | Pairs with the past_due update-billing banner shipped Sep 3 (159fd52) and the renewal reminders.
Social member profiles + the open-or-gated decision | Social members need a profile surface (the four clean fields) and a decision on whether member profiles/cards are open to the public or gated behind login. The public card page exists (card/[public_id]) and already applies the single member-visibility predicate (7084b43); the product decision on what a non-member can see is not made. | Adam decides open vs gated (and what fields are public if open). Then align the public card, the directory and the hub pages to that one rule. Builds on "Strip member profiles to four clean fields" and the privacy toggle row. | WAITING ON ADAM: open or gated | Decision gates part of the hub pages build (which member content the public hubs may show).
Lint warnings someday-audit (475 warnings today, 0 errors) | npm run lint passes with 0 errors but ~475 warnings (unused vars/imports, no-unused-expressions, react-hooks deps). They are noise that hides new real warnings and 17 are auto-fixable. | Someday: run eslint --fix for the auto-fixable set, then burn the rest down file-by-file in otherwise-idle sessions. Never as a big-bang commit; never mixed into a feature change. | Someday | Count as of Sep 21 gates: 475 problems, 0 errors, 17 auto-fixable.
cleanup-business-members: Social product id is a hard-coded constant | cleanup-business-members classifies a customer as business vs social by comparing the subscription's product to SOCIAL_PRODUCT_ID = "prod_TZI8im1xRNUMuy", a constant in the file rather than an env var. A future price/product change would silently reclassify every social member as business — and the function now cancels in Stripe before hiding, so the blast radius of a wrong classification grew with the Wave 10 weld. | Read the id from an env (STRIPE_SOCIAL_PRODUCT_ID, already the name other code uses) with the constant as fallback, and fail closed if neither resolves. Also clear the 3 pre-existing deno type errors in the file while there. Small. | Build — small | Found during the Wave 10 rehearsal, where a wrong product id in the stub made the function (correctly, per its rules) cancel and hide every seeded social member.
stripe-webhook cascade dedupe — point handleSubscriptionDeleted at _shared/membershipCascade.ts | Wave 10 lifted the membership-end cascade (hub seats, people status, credential void + wallet push) into supabase/functions/_shared/membershipCascade.ts for admin-delete-user, but left the webhook's own copies in place so its cancellation path stayed regression-locked. Two copies will drift on the next rule change. | After Wave 10 has soaked: replace the webhook's removeHubSeats / voidPersonCredentials bodies with imports from the shared module, assert byte-identical behaviour with the R4 canned subscription.deleted rehearsal, deploy stripe-webhook. | Build — small, after soak | Same drift class as the comp-invite resolver replica row. Follow-up named in cursor_report_wave10_build.md §6.
IMMEDIATE SPRINT - PRE/POST-EVENT (added Aug 26) - 3 items
Realtime RSVP/cancel sync to Exchange engine + viewer |  |  | Build | RSVPs and cancellations must reflect immediately (no manual refresh) in /admin/exchange viewer (counts, pools, roster) and /admin/exchange/mixer (eligible roster). Candidates: Supabase Realtime subscriptions on attendance_credentials + exchange_intake scoped to the event, or tight polling. Must define cancel-mid-round behavior (current-round seat stands, excluded from next MIX; late check-ins already auto-join next round). Deadline: before Aug 27 event; freeze exception authorized by Adam; full develop rehearsal mandatory, both viewports, simulated RSVP+cancel during an active round.
Exchange mixer/viewer remedy C — shed or wrap columns so the roster fits a 390px phone | R4 shipped remedy B (admin surfaces; header reachable, table cleanly bounded) but the mixer/viewer table is still ~1369px wide and needs sideways scrolling on a phone. Recon remedy C — shedding or wrapping columns — was explicitly left open. | Column-shedding or wrap layout for the mixer roster/viewer at 390px. CSS/markup only; engine untouched. Both viewports on develop before shipping. Adam names which columns can be shed at build time. | Build | Was "mixer engine + viewer spacing fixes". Remedy B landed Sep (R4 build); remedy C is the remaining piece per cursor_report_r4build.md.
Notification bell dropdown cannot scroll |  |  | Build | Member-facing: notification list under the bell is unscrollable, long lists unreachable. Likely overflow-y/max-height on the dropdown container. Both viewports. Low risk; can ride with R4's pass.
ONBOARDING & SIGNUP · 2 items
Collect phone for everyone at signup; gate texts on consent | Phone is captured at signup now; the remaining work is gating SMS on the consent flag (not on whether a number exists) and re-collecting phone from pre-May-21 members whose number was never saved. | Confirm phone persists from signup metadata; gate SMS on the consent flag; add a re-collection prompt for pre-May-21 members. | In Progress | Phone capture + display already shipped; consent gate + backfill remain.
Prompt calendar-subscribe + wallet-pass add at signup | As part of signup, walk the new member through subscribing to the event calendar and adding their wallet pass, so both are set up before they finish onboarding. | Add a calendar-subscribe step and a wallet-add step to the signup / onboarding flow; confirm both stick. | Build | New onboarding-flow ask — pairs with the lifecycle push to current members (see Email & Drip).
MEMBERS & MONEY · 3 items
Verify the payment-to-membership chain end to end | The full money path (checkout -> Stripe webhook -> member activated) has no automated test. | Run a Stripe-CLI end-to-end test of checkout -> webhook -> activation before scaling referrals on it. | Verify | The money path — verify carefully; everything downstream assumes it works.
Verify an email change keeps Stripe billing in sync | When a member changes email, the Stripe customer should update too, so billing/receipts don't split into a second identity. | Change an email; confirm the Stripe customer email updates; no orphaned customer. | Verify | Identity Wave 7 (email sync). Rides BEFORE the mobile app together with Wave 9 (tickets). Internally an email change no longer splits identity (auth_user_id key since Wave 0; contacts family linked at write time since 6C); the Stripe-customer half is the remaining work. Also closes the customer.updated webhook gap noted in the drift-trio recon.
Migrate the 8 legacy $30 subscriptions | The trusted member-count definitions are already established (member_counts view). The only residual is 8 subscriptions still on the retired $30 price. | Move the 8 legacy $30 subs to current pricing in Stripe; $30 is retired everywhere else. | Build | Count reconciliation itself is DONE — this is the leftover cleanup.
IDENTITY FOUNDATION · 1 item
Finish retiring the old ticket tables | RSVP moved to one attendance table; a guest-pass follow-up tracker and one hook still dual-write the old 'tickets' table. | Repoint last guest-pass readers/writers to attendance_credentials, kill the dual-write, drop legacy tickets + guest_passes after a safe soak. | Build | Identity Wave 9 (tickets). Rides BEFORE the mobile app together with Wave 7 (email sync). Wave 9 recon Aug 25 stands: create-guest-pass writes legacy tickets PRIMARY; dashboard guest-pass list + get_community_stats read legacy; capacity trigger pair mapped; retirement order + mandatory backfill (8 of 26 mirrored). Do not drop before the soak confirms nothing else reads them. Closes together with the capacity-trigger split-brain row.
EVENTS & CALENDAR · 19 items
Require an event category at creation | Every event needs a category label at creation (a mis-filed event was shown to the wrong audience). Category is separate from access level. | Two independent fields on the event form — Category (editable label) and Access level — both enforced at creation. | Build | Categories: The 704 / The Reserve / After Hours / The Reset / For the City / The Exchange / Coffee & Connect.
Three event access levels: open / members / business | Production already runs business-only events; the old two-bucket spec needs three: open to all, members only, business-members only. | Implement a 3-value access field driving visibility + RSVP eligibility. | Build | Drives both event visibility and who can RSVP.
One simple event feed everyone sees | Locked: no separate social vs business feeds for now; one feed shows everyone all events. | Ship the single simplest feed; access level still governs RSVP eligibility. | Build | Single feed for now; tiered feeds are explicitly deferred.
Confirm the 118 old calendar links work again | When the feed broke, ~118 members held subscribe-links returning an empty calendar; the June 10 rebuild likely revived them. | Spot-check several of the 118 tokens against the live feed; if events return, close it — else send a re-subscribe email. | Verify | Likely already revived by the June 10 rebuild — confirm, then a soft 'your calendar works' note at most.
Alert if the calendar feed ever goes empty again | The feed broke silently last time. | Cron/health-check comparing feed output to known future events; alert on mismatch. | Build | Catches a silent feed failure like the earlier one.
Verify the event detail page handles every state | Member + public RSVP are verified; waitlist, paid purchase, capacity-full, and cancel/re-RSVP are not. | Test the remaining EventDetail branches. | Verify | Core states already verified; this covers the edge branches.
Verify the RSVP status sidebar shows the right state | Confirm the sidebar reflects all 7 RSVP states. | Walk all 7 states: not RSVP'd, RSVP'd, waitlisted, cancelled, attended, refunded, no-show. | Verify | Purely a verification walk-through; not a build.
Show non-members a teaser of members-only events | A non-member should see members-only events as a teaser: type + 'Members Only' tag, never the location. Creates FOMO, sells membership. | Public view: type + tag, hide name details, always hide location. | Build | Awaiting a fuller public-events-page spec before final build.
Verify the remaining door check-in scan paths | Member check-in is verified; walk-in (no-RSVP) record, guest-pass scan, and junk-scan rejection are not. | Test walk-in QR, guest-pass (GP-) scan, and gibberish-scan rejection. | Verify | Member check-in already verified; this covers walk-in, guest-pass, and bad scans.
Hide all event details until someone RSVPs | By default, all event details are hidden from everyone (even in the portal) except photo, preview name, and date/time; full details reveal only after RSVP. | Default-hide name/location/details; reveal post-RSVP; controlled from the event manager. | Build | Build after the core events work is stable.
Polite no-show email | When a member RSVPs but doesn't show (known from check-in), send a kind 'only RSVP if you can attend' email — resources are planned around counts. | Trigger off check-in data (RSVP'd + not scanned = no-show). | Build | Depends on stricter RSVP + solid check-in data.
Persist public RSVP confirmation + on-page QR | When a non-member RSVPs, keep them confirmed on reload and show their QR on the confirmation page (+ email); no account required. | Persist confirmed state on reload; render QR on the confirmation page + email. | Build | No account creation for the public RSVP — just persistence + QR.
Optional event host (name + photo) | Let an event optionally show a host with name and photo. | Event host field + admin form + display. | Build | Simple optional field; no dependencies.
Future-event visibility limits | Define and enforce how far ahead events are visible (date range, tier, or capacity). | Scope the limit dimension, then enforce. | Build | Decide the limit dimension before enforcing.
Soft-delete for events | Let events be recoverable rather than hard-deleted. | Soft-delete events. | Build | Related to the event-DELETE RLS failure that the identity fix resolves.
Self-serve event management | Let hosts/business members propose or manage their own events (admins publish). | Define permissions — likely 'propose -> admin publish'. | Build | Needs scoping before build.
Event reorganization | Restructure how events are displayed per the events direction. | Needs the detailed events-page spec. | Build | Blocked on the detailed events-page spec.
Calendar scope picker in settings | Optional: let business members narrow their calendar to business-only. | Implement only if tiered feeds return. | Build | Optional given the single-feed decision; only relevant if tiered feeds return.
Instant Google Calendar updates | Subscribed calendars refresh every 8-24h; true instant needs a Google Calendar API push integration. | Service account writing to each member's calendar. | Build | Larger effort — a Google Calendar API push integration.
WALLET PASS · 5 items
Verify Apple Wallet passes work on real phones | Confirm generate, deliver (dashboard + email), and update-on-status-change end to end; code is further along than expected. | Test on a real iPhone; fix gaps. | Verify | Generation + push-update already exist — verify on a real device, then close gaps.
Kill a membership pass when someone cancels | When membership lapses/cancels, the pass must stop scanning at the door; a void function exists. | Verify cancellation voids the pass and it dies on-device. | Verify | Nothing should scan at the door after membership ends.
Give members a QR backup if their pass fails | Door failure modes: dead battery, no signal, deleted pass. | Dashboard QR fallback + 'resend my pass' button. | Build | Assume bad connectivity at the door.
Complete Google Wallet passes | Bring Google Wallet to parity with Apple (generate/deliver/update); the scaffold is partial. | Finish Google Wallet generation + delivery + update. | Build | Scaffold is partial; bring to parity with Apple.
Apple Wallet push notifications + email attachment | Push on changes + pass-as-email-attachment. | APNs push + email attachment. | Build | After pass voiding is working.
AMBASSADORS · 5 items
Verify the referral price applies at checkout | Confirm the $35 ambassador-referred social price applies via a referral link (vs $49). | Confirm referral checkout shows $35. | Verify | Checks the $35 referral price vs the standard $49.
Build the manual payout queue UI | An admin UI to review and release ambassador payouts. | Payout queue UI for admins. | Build | Where an admin reviews and releases payouts.
Ambassador leaderboard | A leaderboard ranking ambassadors by referrals. | Ambassador leaderboard. | Build | Ranks ambassadors by referrals.
Read-only ambassador tab | A view-only tab for ambassadors to see their own referral activity. | View-only ambassador tab. | Build | Ambassadors see only their own activity.
Unified admin users view (members + ambassadors) | One admin view combining members and ambassadors. | /admin/users unified view. | Build | Combines members + ambassadors in one admin view.
MEMBER TEXTING · 2 items
Confirm we're cleared to send texts (Twilio A2P 10DLC) | Records conflict on whether A2P 10DLC is approved; one call to Twilio settles it. Gates all texting. | Confirm A2P 10DLC status directly with Twilio; assign an owner + date. | Blocker | Nothing SMS ships until this is confirmed.
Build the portal-baked texting inbox (Charlotte number, shared, consent + STOP) | All member texting runs through ONE Charlotte-based Twilio number wired into the admin portal — no managed third-party tool, and no text ever reaches a personal phone. Inbound messages hit a webhook, write to our database, and appear in a shared team inbox where every co-founder can read and reply; replies send from the club number. Consent and STOP are enforced and stored on the canonical person record. | Twilio number -> inbound webhook (Edge Function) -> DB -> portal Messages inbox (threads per member) -> reply sends from the club number. Enforce consent + instant STOP; log idempotently before send; dedup in one shared send function. Inbound triggers an alert (email + the in-portal notification bell). Standard outbound: welcome, Monday digest, day-before reminders, week-1/2 nudges. Layer 1 only — no AI agent. Burn in 5-7 days. | Build | HARD REQUIREMENT: nothing lands on a personal cell; fully transparent + team-managed. Gated on the A2P confirmation, the phone-storage model, and the identity foundation.
SECURITY · 2 items
Rotate the shared admin password before the developer starts | The super-admin password was shared in working sessions; rotate it before any third-party developer gets repo/dashboard access. | Rotate super-admin + test-account credentials before granting access (~10 min). | Blocker | Owner task — a prerequisite before onboarding the developer.
Rotate and remove secrets committed to the code | Live GroupMe join tokens were committed to git history; the file was deleted but the tokens stay readable until rotated. | Rotate the exposed tokens (rotate-only, no history rewrite). | Blocker | Rotate so the committed copies become useless; no history rewrite.
SECURITY & MONITORING · 5 items
send-email service-role auth: replace SB_SECRET_KEY duplicate with verified getClaims check | On 2026-08-12 the sb_secret_ prefix grant and the unverified-JWT-payload grant were removed from send-email and ambassador-payout (both were forgeable). That broke every restricted-template send on prod for about 10 minutes, because the app's legacy eyJ service-role JWT does NOT equal the SUPABASE_SERVICE_ROLE_KEY the function runtime sees - it had been passing via the unverified decode all along. Mitigated by setting SB_SECRET_KEY on prod to the same legacy JWT the app sends, restoring an exact match. That works but stores one credential under two names. | Replace the SB_SECRET_KEY exact-match branch with supabase.auth.getClaims(token) plus a claims.role === 'service_role' check. getClaims verifies the signature, so it is not forgeable, unlike the removed base64 decode. Confirm a user-scoped token can never surface role service_role in verified claims before relying on it. Then delete the SB_SECRET_KEY secret from prod. CRITICAL: test with the REAL prod service-role key against PROD before deploying - develop cannot catch this class of bug because develop's key is the new sb_secret_ format which the gateway rejects outright. Restricted templates affected if this breaks again: password-setup, welcome-new, welcome-back, welcome-setup, guest-pass, admin-invite, public-rsvp-confirmation and 22 others. | Build | Raised 2026-08-12 after causing and resolving a live 10-minute prod outage on restricted-template email. Prod currently healthy via SB_SECRET_KEY. Verified: Vercel prod and .env.local hold the same 219-char legacy JWT.
Dead trigger: last_attended_at never updates from public check-ins | The trigger trg_update_last_attended_from_public_rsvp fires on event_public_rsvps check-in and is meant to stamp profiles.last_attended_at. It looks up contacts.converted_to_member_id first, and NO code anywhere writes that column (0 of 207 rows on prod have it set), so the trigger always exits early. Members who check in through the public RSVP path never get their last-attended date updated. | Two options. Either populate contacts.converted_to_member_id when a contact becomes a member (a real CRM flow that does not currently exist), or rewrite the trigger to resolve the profile by email or through the people bridge instead of the dead column. The second is far smaller. Note the conversion-rate report widget that depended on the same column was removed on 2026-08-12 because it always rendered 0 percent. | Build | Raised 2026-08-12 during a contacts table audit. Fails safe - does nothing rather than something wrong.
Add a deploy pipeline so changes go live safely | DB/function changes are pushed by hand today — the root cause of code/live drift. Locked: hand-patching stops once this lands (with a written emergency lane). | GitHub Actions: merge to main -> db push + functions deploy. Needs 3 repo secrets. | Build | Once in, hand-patching stops; needed before two people touch production in parallel.
Make the code able to rebuild the live database | Several live DB objects were made by hand and aren't in migration history, so the repo can't recreate prod. | Snapshot prod schema, diff vs migrations, commit a baseline migration. | Build | Absorbs recent hand-made objects (RSVP backfill, a few functions, the unsubscribe function).
Add three safety tests on the things that can't break | Effectively no automated testing exists. | Three critical-path tests — (1) checkout -> webhook -> activated, (2) RSVP -> attendance, (3) unsubscribe honored — and remove passWithNoTests so CI gates. | Build | The three failures that hurt most; flips CI from passing with zero tests.
EMAIL & COMPLIANCE · 3 items
Make every email sender respect unsubscribes | The unsubscribe page/link policy is fixed, but two senders (drip processor, renewal reminders) still don't check the opt-out flag, and one reminder may skip members on a null value. | Add opt-out filtering to process-drips + renewal-reminders; fix event-reminder null handling. One opt-out flag is the source of truth. | In Progress | send-email unsubscribe-block work is in flight; process-drips + renewal-reminders filtering to confirm/finish.
Make unsubscribe links forgery-proof | The unsubscribe token is currently guessable/forgeable (low stakes). | HMAC-sign the token; align format across send-campaign, send-email, and unsubscribe. | Build | Align the token format across the three places that generate/read it.
Remove unsubscribe links from ALL emails; members cannot unsubscribe (manual-only)
ADMIN & OPERATIONS · 9 items
Add a private notes section on each member | Internal request: a notes area per member for context (e.g. 'comped through August'). | Read: admin + super-admin. Write/edit: super-admin only. Not member-visible. | Build | Internal-only; super-admin writes, admins read, members never see it.
Build the admin health dashboard | One screen showing system health at a glance; catches silent failures before members do. | 5 widgets — cron, webhooks, drip health, email tracking, payment sync. Sits on /api/health. | Build | Reads /api/health + checks; surfaces silent failures.
Let admins change a member's tier and have billing follow | App-side tier change/comp exists; the Stripe billing side doesn't follow. | Wire admin tier-change to Stripe subscription cancel/modify/start. | Build | App-side override already exists; this is the Stripe billing reconciliation.
Harden the admin cancel-subscription flow | Make admin cancel safe (running twice shouldn't double-act). | Add idempotency + structured logging + alert to admin-cancel-subscription. | Build | Idempotent + logged + alerted so a double-run can't double-act.
Build the admin area into clean sections | Reorganize admin into Today / People / Events / Network / Money / Messages / Settings with one source of truth per question. | 7-section IA; folds in nav cleanup, per-event check-in start, financial accuracy, tier tools, and guest upload. | Build | The Messages section is where the texting inbox lives.
Shared admin navigation config | One shared config for admin nav so it's consistent and not duplicated. | Single adminNav config; remove duplicated nav definitions. | Build | One config; removes duplicated nav definitions.
Guest list upload tool | Let admins upload a guest list for an event. | Guest list upload UI. | Build | Also unblocks future guest-conversion automation.
Fix the organization settings table | organization_settings has the wrong schema. | Correct the organization_settings schema. | Build | Schema is currently wrong; correct it.
Route Stripe receipts to the team inbox | Receipt/invoice emails should also go to hello@704collective.com. | Stripe email settings -> CC hello@ (or a forwarding rule). | Build | CC hello@ on Stripe receipts, or add a forwarding rule.
MEMBER EXPERIENCE · 9 items
Strip member profiles to four clean fields | Simplify the profile to name, photo, what you do, and a one-line bio — as real columns, not JSON. Locked: archive the other 15+ fields (kept in DB, hidden) for future matchmaking. | 4 visible fields as real columns; align onboarding + settings + directory. The 4-field data move rides with the identity foundation (same plumbing). | Build | Archive (don't delete) the rest — raw material for future matchmaking.
Build the one merged member portal with tiered views | Locked: replace the two portals (member dashboard + business portal) with ONE codebase; business gets an elevated view, social the standard view; clear type distinction preserved. | One portal codebase; gate business-only modules behind member type. Replaces /dashboard vs /business-portal. | Build | Replaces /dashboard vs /business-portal with one tier-gated codebase.
Rebuild onboarding questionnaire + member brief | Store responses in their own table and generate a 'member brief' for future matchmaking/AI. | Onboarding rebuild + onboarding_responses table + member_brief column. | Build | Responses in their own table; feeds a future member brief.
Member portal / dashboard redesign | The redesign: 5-tab bottom nav, pass-first / next-event hero, onboarding checklist removed after completion, plus resources/bookings tabs. The shared activity feed is KEPT and built on (members post / share / like; event discussions surface there) — only the minor personal activity-log widget from the old dashboard is retired. | Multi-week. SEQUENCING: the visual redesign lands AFTER the identity foundation is built and verified — not concurrent with it (one big change at a time on a no-staging system). Resources/bookings depend on vendor partnerships. | Build | Activity feed stays; only the personal activity-log widget is retired. Visual redesign sequenced after identity.
Member directory — people-finder for all member + partner types | A members-only people-finder where social members, business members, and partners can all find and see each other — profiles only, WITHOUT the business-listings view. Visible to everyone logged in, regardless of type. A privacy toggle lets a member hide from it. | Logged-in directory of people (social + business + partner). Profiles only — no business view (that lives in The Network). Visible to all logged-in types; honor the privacy toggle. | Build | Distinct from The Network (hubs + business/partner listings). Pairs with the privacy toggle below.
Profile privacy toggle | A toggle for members to control whether they appear in the directory and the internal Network member view. | Build the opt-out toggle; default is listed, members can hide themselves. | Build | Confirmed feature — the directory is opt-out via this toggle.
Member cancellation retention flow | Improve the cancellation flow with retention UX. | Retention UX on cancellation (offers, pauses, feedback). | Build | Offers / pauses / feedback on cancellation.
Member spotlight on calendar/home | Feature a member spotlight on the calendar/home pages. | Member spotlight feature. | Build | Feature a member on calendar/home.
Unlimited guest passes for dream-team members
PERFORMANCE · 5 items
Speed up slow list pages (Events, Tasks, Hubs) | These pages make many small repeated DB calls (N+1) that get slow as data grows. | Resolve the N+1 query patterns; batch them. | Build | Batch the repeated calls on Events, Tasks, Hubs.
Make bulk member adds all-or-nothing | Bulk add isn't transactional — a partial failure leaves half-written data. | Make add-members and hub-delete atomic. | Build | All-or-nothing; same for hub deletes.
Move heavy admin queries to the server | Keep the browser from doing heavy lifting on admin overview + email dashboard. | Add server-side RPCs: admin_overview, email_dashboard. | Build | Move admin overview + email dashboard to server RPCs.
Standardize how data is loaded (React Query) | Make loading behavior uniform and reliable. | React Query rollout across data fetching. | Build | Uniform data-loading / caching across the app.
Audit shortcut data fields for correctness
AUTH · 7 items
Verify magic-link login across two devices | Phone-to-desktop: request a link on a phone, type the 8-digit code on the desktop. | Cross-device OTP test; confirm same-device + resend cooldown too. | Verify | Requires a second device (owner-run).
Verify magic-link login works in production | End-to-end check the email magic-link round-trip works live. | Test request -> click -> signed in, in prod. | Verify | End-to-end live round-trip check.
Verify sessions refresh correctly on expiry | Confirm cookie-based refresh works when a token expires so members aren't kicked out. | Verify @supabase/ssr middleware refreshes session on token expiry. | Verify | Confirm members aren't kicked out when a token expires.
Verify Google sign-in works | Confirm Google login/signup paths work in production. | Test Google OAuth signup + sign-in. | Verify | Confirm Google login/signup in production.
Apple Sign-In
Branded auth links (stop showing supabase.co URLs) |  |  | Build
Password rules hardening (min length 6 to 8, leaked-password check) | Supabase minimum password length is 6 and the leaked-password check is off. Both are weaker than they should be for a paid membership platform. | Do the UI copy FIRST, then the dashboard toggles. Update /setup-password and every password field to state the real rule before raising the server minimum to 8, otherwise members get rejected by a rule the screen never showed them. Then enable Prevent use of leaked passwords and confirm the rejection message renders cleanly. Leave Require current password when updating OFF, it breaks the no-password comp-invite setup flow. Rehearse on develop both viewports. | Build | Raised 2026-08-06 during the Email OTP expiration change (3600 to 86400).
BUSINESS · 1 item
Verify the business application approval works
FINANCIALS · 5 items
Verify the financial dashboard | Confirm it reports MRR, churn, and revenue by tier correctly (churn once showed 2055%). | Verify financial dashboard accuracy. | Verify | Built in Lovable originally — accuracy unconfirmed.
Verify the admin financial data function | Confirm the edge function feeding admin financials returns correct numbers. | Verify admin-financial-data. | Verify | Confirm the numbers it returns are correct.
Three-bucket revenue view | Show revenue split three ways. | Collected / projected / churned split. | Build | Collected / projected / churned.
Member-facing financial widget | A small financial widget members can see. | Member-facing billing-status widget. | Build | Small billing-status widget for members.
Reduce redundant Stripe scans | Cut how often the system scans Stripe, for performance/cost. | Reduce Stripe API scan frequency. | Build | Cut scan frequency for cost / performance.
EMAIL & DRIP · 13 items
Drip email health banner | A banner flagging when drips are silently failing or stalled. | Drip health-check banner. | Build | Flags silently failing / stalled drips.
Guest follow-up drip (7 + 20 day) | Automatic emails to guests at day 7 and 20 to convert them. | Guest 7-day + 20-day drip. | Build | Converts guests at day 7 and 20.
14-day RSVP prompt for new members | Nudge new members who haven't RSVP'd within 14 days. | 14-day RSVP prompt drip. | Build | Nudges new members who haven't RSVP'd.
Confirm the email log matches actual sends | Today failures are swallowed; make 'did this send' provable. | email_log row matching; stop swallowing failures. | Build | Stop swallowing failures so 'did this send' is provable.
Per-email open/click analytics | Track opens/clicks per template so we know what works. | Per-template email analytics. | Build | Per-template open / click tracking.
Per-member engagement scoring | Score each member's engagement from email/event activity. | Engagement scoring per member. | Build | Score members from email / event activity.
Category-level unsubscribe preferences | Let members opt out of specific categories, not all-or-nothing; builds on the one-flag fix. | Per-category opt-out prefs + a member settings page. | Build | Builds on the one-flag opt-out fix.
Branching drips based on opens/clicks | Drip sequences that branch on open/click. | Open/click-branching drips. | Build | Branch sequences on open / click.
Send email from a contact record | Let an admin email directly from a member/contact record. | Send-email action on the contact record. | Build | Admin emails directly from a member record.
Attachments and images on event email campaigns | Let campaign emails include attachments and images. | Extend the campaign editor for attachments + images. | Build | Extend the campaign editor.
Live test the guest-pass drip | Confirm the drip fires correctly on a guest pass. | Live test the drip on guest_pass. | Verify | Confirm it fires on a guest pass.
Merge guest follow-up into the drip processor | Retire the separate guest-followup function and fold it into the main processor. | Consolidate guest-followup into process-drips. | Build | Fold guest-followup into process-drips.
Push current members to subscribe to the calendar + add their pass
DATA & CLEANUP · 5 items
Add CHECK constraints incrementally (enums REJECTED — too risky) | Was 'convert status text -> enums'. DIAGNOSED Jul 9 as too risky: ~35 tables / 60+ write paths, and profiles.subscription_status is fed by the Stripe webhook with Stripe's full status vocabulary (trialing/paused/incomplete/etc). An enum built from observed values would make the webhook UPDATE throw on the first unseen status — silent breakage in the PAYMENT path. Enums rejected. | If typo-prevention is wanted later: add per-table CHECK constraints (NOT enums), table-by-table, starting with attendance_credentials (values: active/used/voided). Trivially reversible. Its own scoped task — never wholesale. | Deferred | Reclassified Jul 9. Do NOT rush — payment-path risk. CHECK constraints are the safe 80/20 if revisited.
RSVP attribution by event ID | DIAGNOSED Jul 9: bigger than 'add a column'. Per-event RSVP tagging is DEAD — the code that slug-tagged events was removed; since Apr 21 a public RSVP only gets a generic 'free-event-rsvp' tag, so you can't segment 'RSVP'd to event X' for any recent event. 6 frozen slug-tags remain (105 rows) and rot on rename. contact_tags has NO event_id column. | HALF-DAY scoped task (not a quick close): (1) migration add nullable event_id uuid REFERENCES events(id) to contact_tags; (2) re-add per-event tagging in capture-public-rsvp (event_id already in scope) + optionally create-guest-pass; (3) backfill — 5 of 6 slug-tags map to real event_ids by title-slug match (1 unmatched: coffee-and-connect-tabbris-co-working). Deploys + tests. | Build | Jul 9: revives dead per-event attribution. Own task, budget a half-day. Backfill mostly possible.
Drop ~35 empty leftover tables | ~35 empty scaffolding tables (old CRM, social manager, feed, DMs). | Export copies as a receipt, then drop. | Build | Don't drop without exporting copies first.
Backup tables: keep or drop — Adam's call (13 hand-made snapshots; auth-hash pair flagged) | cursor_report_rlsaudit.md (Sep 21): 13 hand-made backup tables from Apr–Jun 2026 remain in public (presweep x7, 20260610 x4, _auth_*backup_20260428 x2). Nothing references them; RLS deny-all holds and the leftover anon/authenticated grants were stripped on prod (by hand) and develop (migration 20260921070000). _auth_backup_20260428 holds old_encrypted_password for 24 users — the one pair that should not linger. backup_ambassador_referrals_presweep is empty. | Adam decides per snapshot whether its purpose is closed. Suggested order: the two _auth_* tables (export with pg_dump -t if a cold copy is wanted, then drop), the empty ambassador backup, then the presweep/20260610 sets once the identity sweep and sauna merge are considered settled. No drops proposed in SQL without provenance. | WAITING ON ADAM: keep or drop | Security posture is already correct (grants stripped, 17/17 receipt). This row is hygiene + the password-hash pair. Provenance for all 13 is the July baseline dump only.
Delete dead admin member components
MARKETING & FRONT-END · 9 items
SEO + schema markup + pre-rendering (all front pages + 4 hub landers)
Homepage hero rebuild + image optimization | Rebuild the hero and compress oversized hero images (currently 24-30MB, should be 200-800KB). | Hero rebuild + compress images. | Build | Includes compressing 24-30MB hero images to 200-800KB.
Homepage copy rewrite + slogan | Rewrite homepage body/section copy and update the slogan. | Body + section copy + slogan. | Build | Needs the copy spec.
Fix the mobile hero sliding bug | A visual bug where the hero image slides on mobile. | Mobile hero sliding fix. | Build | Fix the hero sliding on mobile.
The Exchange page | Build The Exchange page (speaker-driven business event product page). | The Exchange page. | Build | Speaker-driven business-event product page.
Sponsor page (likely folds into /business) | Sponsor functionality — likely folds into the /business application routing. | Probably absorbed by the /business rebuild. | Build | Likely folds into the /business rebuild — confirm first.
/business page rebuild with dynamic application | Rebuild /business as one page with a dynamic application routing prospects to membership, Preferred Business, or sponsorship by their answers. | Dynamic diagnose-before-offer application. | Build | Routes prospects to membership, Preferred Business, or sponsorship.
The Network — four hubs + members rolled up | The four hubs rolled up into one view, plus all members. Two faces reading the same data: a PUBLIC face (the hub landers + business/partner listings — the sales asset) and an INTERNAL in-portal view that rolls up everyone. Social members appear ONLY on the internal in-portal view — never on the public hubs. | Roll the four hubs into one Network view + members. Public face = hubs / business + partner listings (social members excluded). Internal face = full rolled-up view including social members. Reads the same hub data as the landers. | Build | Depends on the portal + identity foundation. Social members are internal-only on The Network. Separate from the member directory (people-only).
Instagram comment auto-DM (ManyChat)
AI / AGENTS (LATER EFFORT) · 2 items
AI concierge + agent platform
AI foundations (memory, embeddings, coordination) | Supporting infra for the agents: shared memory, member embeddings, multi-agent coordination, model routing. | pgvector + embeddings, agent_memory, multi-agent coordination, model routing. | Build | A later effort; supports the agents (embeddings, memory, routing).
EVENT DISCUSSION & NOTIFICATIONS + JUL-5/6 FINDINGS — IN-HOUSE (NOT ON THE DEVELOPER SHEET) · 5 items
Rotate the R2 media token (exposed key) | The R2 Access Key ID + Secret for bucket 704-discussion-media were exposed in a working chat (screenshot/paste). Scope = that one media bucket only — low blast radius, but rotate. | After 6c ships: Cloudflare -> R2 -> API tokens -> re-create 704-discussion-upload (Object Read & Write, bucket-scoped) -> supabase secrets set the two new values -> confirm an upload still works. | Declined | Adam declined rotation Jul 5 - standing watch item. Key scope = one media bucket only (no member data / money / DB). Say 'rotate' anytime: ~2 min.
Verify/finish the Alerts page (full history, discussion types) | Locked: bell badge clears on open, items dismiss via X, but the ALERTS PAGE keeps every notification forever - markable read (single + all). PARTIAL Jul 5: /dashboard/notifications now honors action_url (deep-links verified end to end). Remaining: full-history + mark-read behavior verification. | Read the Alerts page code; verify full-history + mark-read behavior and that all discussion notification types display with correct deep-links; fix gaps. Desktop + mobile test. | Verify | Deep-links fixed+verified Jul 5 (commit e9f6250). Remaining: verify full-history retention + mark-read (single + all).
Messaging: bells for messages in existing conversations | Messaging was resurrected Jul 5 (DMs/groups had NEVER worked since launch: RETURNING/RLS deadlock, participants-insert policy tautology, content-vs-body + title-vs-name schema mismatches, 4 missing messages columns - all fixed and verified end to end). Remaining gap: notifyNewConversation only fires on conversation CREATION, so messages into an existing thread produce no bell. | Add a new_message bell per message into an existing conversation, throttled (e.g. skip if an unread new_message bell for that conversation already exists). | Build | Follow-on to the Jul 5 messaging resurrection. Recipients currently only get notified on the first-ever message.
Messaging: attachment uploads (images/files) | MessagingView has image/file upload code paths and messages now has image_urls/file_urls/file_names columns (added Jul 5), but the storage wiring (bucket, upload flow) has never been tested and may not exist. | Audit the attachment path end to end: storage bucket, upload call, render. Fix or wire what's missing. Desktop + mobile test. | Build | Text messaging + edits verified Jul 5; attachments explicitly skipped in that test.
Verify the first real-money admin refund (Remove & Refund) | Admin Remove & Refund shipped Jul 5 (edge fn admin-refund-ticket: admin gate, Stripe refund, void credential, seat freed; + attendee-dialog button, mobile-safe). Every branch proven EXCEPT the successful real-money refund line: void-only path, 403 gate, already-voided idempotency, and the Stripe-failure 502 fail-safe (no seat freed without money returned) all tested live. | WAIT mode: on the next genuine member refund request, use Remove & Refund in the event attendee dialog and verify: Stripe refunded, credential voided, seat freed, toast correct. | Verify | Zero-cost proof on the next real request. Sacred Walker (Jul 5) handled manually pre-feature; her case is the template.
SESSION LOG — JUL 7–9 2026 (COMPLETED; kept as record, esp. the security fix)
[DONE] Security: dropped anon-readable active_members view + locked event_participants_view | CRITICAL FIX Jul 9: active_members and event_participants_view were SECURITY DEFINER views with ALL privileges granted to anon — an unauthenticated internet caller could read every member's email/phone/Stripe customer ID + all attendee contact info, AND active_members (auto-updatable single-table view) exposed an anon WRITE path into profiles. active_members had ZERO callers -> DROPPED. event_participants_view -> security_invoker=true + REVOKE anon/authenticated (sole caller send-campaign uses service-role, unaffected). member_counts left as-is (intentional). | DONE via SQL. Verified from OUTSIDE with anon key: active_members=404, event_participants_view=401 permission denied. No rows leaked. send-campaign confirmed still works. | Done | Biggest find of the session. Was disguised as a 'review Security Definer flags' tracker row.
[DONE] Nine-job cron auth resurrection + 2 guards, all 10 jobs healthy | Full audit found NINE broken crons (sheet knew of 2). Fixed: Vault key was legacy JWT but runtime injects sb_secret_ (updated Vault); SQL typo value->decrypted_secret on jobs 3/4/13; event-reminder had no service-key path + a no-auth-header mass-email hole (both fixed, commit 09d637d). Then built 2 guards: business-profile-reminder 14-day cooldown via contact_activity + internal-account exclusion (503548c); guest-event-match at-capacity exclusion (d722800). Both jobs 2 & 10 re-enabled. All 10 cron jobs now active + healthy. | All confirmed 200 on live ticks. Guards dry-run/logic verified. WATCH: first live ticks of job 2 (14:00 UTC every 2 days) + job 10 (13:00 UTC daily) — read-only confirm right people emailed. | Done | Commits 09d637d, 503548c, d722800 + Vault + SQL. event-reminder security hole closed.
[DONE] Sentry error monitoring — live + verified in prod | @sentry/nextjs wired (client+server+API+global-error), CSP allowance, instrumentation moved into src/ (Next ignores root-level with a src/ dir), DSN + source-map auth token in Vercel, /admin/sentry page activated. Prod capture VERIFIED (smoke-test error landed in feed). | Verified. WATCH: confirm Sentry project SLUG is exactly '704-collective' in a Vercel build log (source-map upload) — if wrong, traces stay minified (one-word fix). | Done | Commits 417fb37/d779885/5d12aac/b437166. The safety net — Stage 1 complete.
[DONE] Josh Ahart full removal (exit workstream) | De-privileged (super_admin->lead), permanent ban, all 8 sessions + 64 tokens killed, profile deactivated, ambassador row disabled, removed from public /about page (0cc8c66), 2 dormant test dupe accounts hard-deleted. Stripe sub cancelled + Connect account rejected (Adam, dashboard). Platform passwords rotated (Adam). | Verified: role=lead, 0 sessions/tokens, banned. Public site scrubbed. Dashboard-member removal confirmed by Adam. | Done | NOT on the build sheet — exit workstream. Recorded here for completeness. Aug 25: Josh hub purge DONE - his 4 remaining hub_members rows (one per hub, all joined 2026-05-21 03:11:32, all added by Adam) were deleted; verified afterwards at 0 hub memberships, 0 posts, 0 comments, 0 likes, 0 resources. CORRECTION to an earlier wording of this note: Josh created NO hubs. All four hubs are created_by Adam, so nothing was owned by him and the purge was membership rows only - the cascade risk on hubs.created_by is a separate finding about Adam's profile (see that row). Also noted while verifying: the hub display queries in dashboard/hubs/[id] and admin/hubs join profiles without a deleted_at filter, which is why his soft-deleted profile kept rendering and inflated each hub's member count by one. Closes the hub residue of the exit.
[DONE] Member status batch (Jul 9) | Nicholas Stathopoulos + Robert Villante -> non_member/inactive/override off/lead (Nick admin revoked + sessions killed). Whitney Cleland + Brenna Dunne + Kaelah Torres -> ERASED (auth+profile+people+credentials deleted; all comped, no Stripe to cancel). More status changes flagged as coming. | All verified via SQL (zeros on erase). Read-first footprint audit confirmed safe (no owned content cascaded). | Done | Adam noted more member changes coming next session. Aug 25: Audrey Handleton converted to non-member - DONE, and recorded here as the next entry in this running member-status record. Verified end state: profiles reads non_member / inactive / membership_override false; the people row reads roles ['prospect'] with member_tier and member_status both null (never-was, not canceled). She was a comp who had drifted - profile said social while her people row still said business - and she never paid a cent, so there was no Stripe side to cancel.
[DONE] Business-event RSVP tier leak — closed + Annslee voided | Social members could RSVP business-only events: create-member-rsvp never checked required_tier, and the mobile sticky RSVP bar bypassed the desktop gate. Fixed: server-side tier gate in the edge function (ff20ba9, admins exempt) + mobile CTA respects canRsvp (952fbb2). Annslee Bottoms' live breach credential on Jul-14 Business Member Meeting VOIDED. Past legacy breaches intentionally left (real attendance history). | Verified: socialtest gets 403 'business members only' + red toast; direct-invoke blocked; Annslee active count on event = 0. | Done | Commits ff20ba9, 952fbb2. Guest-side email opt-out gap noted -> folds into unsubscribe policy work.
[DONE] Discussion edit/delete (comments+posts+photos) + admin always-on access | Owners + admins can now edit/delete their own discussion comments (ecec3f8), posts (1e3adc1), and remove their own gallery photos (bcf746f); admins moderate anyone's. '(edited)' marker, soft-delete, silent removal. Also: admins now see the discussion link on any open event regardless of RSVP (583b343 — backend was already admin-exempt; was a missing-link discovery bug). Feed/comment/DM URL linkify (561403e). | All browser-tested desktop+mobile. Backend RLS already permitted; these were frontend gaps. | Done | 5 commits. Discussion feature now fully moderatable.
[DONE] Small fixes: hubs 404, week_label, dead components, partners 400, org_settings, last_attended | hubs preview widget queried non-existent 'business_hubs' -> fixed to 'hubs' (a00cc50, restored a silently-broken business-tier feature). ambassador-payout phantom week_label column removed (1f46e88). 3 dead admin components deleted, 1376 lines (306efa4). partners 400 fixed via column aliasing (d95a337, latent partner-disappearing bug). organization_settings tracker row was STALE (schema fine, closed). last_attended already built+firing -> backfilled 17 pre-trigger rows, closed. | All tsc+browser verified. org_settings & last_attended were already-done rows. | Done | Commits a00cc50, 1f46e88, 306efa4, d95a337 + 2 SQL closes.
PHASE 2 · MAJOR BUILDS (each gets its own detailed scope before build)
MAJOR BUILDS — EACH GETS ITS OWN DETAILED SCOPE BEFORE BUILD · 5 items
CRM system | Full customer-relationship system built ON the merged person record: 360-degree member view, segments/audiences, lifecycle tracking. The internal data model IS the CRM (not a re-introduced external tool). | Own detailed scope before build. | Phase 2 | Built on the canonical person record from Phase 1. Currently hidden behind the reversible HIDE_CRM_AND_PARTNERS middleware flag (carve-out keeps /admin/crm/campaigns live for the newsletter).
Preferred Business Network | New paid product: vetted local-business listings, $300/mo to be listed. Lives in the portal first, public domains later. Includes the internal 'Seats' system. Social members browse this to find services. | Own detailed scope before build. | Phase 2 | Plugs into The Network surface built in Phase 1.
Partner Portal (audit, then repurpose or remove) | An existing, mostly-built partner portal of unclear purpose. Audit it, then either repurpose it as the Preferred Business Network management surface or remove it. Frozen until then. | Own detailed scope before build. | Phase 2 | Audit first; likely becomes the Preferred Business Network management surface. Currently hidden behind the reversible HIDE_CRM_AND_PARTNERS middleware flag.
Shared email inbox view for super-admins | A shared inbox view so super-admins can see the team email (hello@) in one place. | Own detailed scope before build. | Phase 2 | Super-admin visibility into hello@.
Corporate / bulk-sales floating-seats portal | A portal for selling memberships in bulk to companies, with reassignable 'floating' seats. | Own detailed scope before build. | Phase 2 | Reassignable floating seats for companies.
OPEN WATCH ITEMS — ADDED 2026-07-19 · 6 items
Refill the Vercel NEXT_PUBLIC_TURNSTILE_SITE_KEY value (hardcode fallback active) | The prod env var was set to an empty string, which made the Turnstile widget render nothing and locked members out during an incident. A hardcoded public site-key fallback in TurnstileWidget.tsx currently masks the missing value. Fallback fails CLOSED (blocks rather than bypasses); the code docstring claims the opposite and is wrong. | Set the real public site key for NEXT_PUBLIC_TURNSTILE_SITE_KEY in Vercel (production), redeploy, confirm the widget renders from the env var, then optionally remove the hardcoded fallback. | Build | Public site key (safe): 0x4AAAAAAD3gqCivsYyImeUH. Fallback keeps login working today; refill so config isn't hidden in code.
Resolve the capacity-trigger split-brain (tickets vs attendance_credentials counting) | Event capacity is enforced by triggers on two tables (attendance_credentials and legacy tickets) that count independently, so the seated count can disagree depending on the write path. | Pick one source of truth (attendance_credentials); make both trigger families count consistently, or retire the legacy tickets capacity path once tickets is fully retired. Coordinates with 'Finish retiring the old ticket tables'. | Build | Closes with identity Wave 9 (tickets), which now rides before the mobile app. The admin_override bypass spans both trigger families; the counting split remains until tickets is retired.
Delete the stray Stripe Connect account | A leftover Stripe Connect (Express) account from the ambassador / exit workstream needs removing so it doesn't linger. | Confirm the account has no pending balance or payouts, then delete/reject it in the Stripe dashboard. Owner task. | Build | Cleanup item from the ambassador / Connect work; low blast radius.
ManyChat - disconnect the Instagram-side integration | The IG-side ManyChat connection needs to be disconnected / cleaned up. This is teardown of the current Instagram link, separate from the auto-DM build. | Disconnect the Instagram account from ManyChat (owner task in ManyChat / Meta); confirm no active automations still reference it. | Build | Distinct from the 'Instagram comment auto-DM (ManyChat)' build row above - that row stays as-is.
DB / Stripe drift watch items | Ongoing watch on the places where the database and Stripe can drift out of sync: subscription statuses, customer email on email-change, retired legacy prices, orphaned Stripe customers. | Track and periodically reconcile; surface on the admin health dashboard. Pairs with the Q6 tripwire and the 'email change keeps Stripe billing in sync' verify. | Watch | Status drift is now DETECTED nightly by stripe-drift-check (Wave 10, live Sep 18: drift_checks receipts, super-admin bell + email on ghost-member / still-billed shapes; first manual run on prod was clean, 0 alerts). Remaining watch items here: customer email on email-change (Wave 7), retired legacy prices, orphaned Stripe customers. Payment-ledger drift is the Financial Truth phase 3 row.
Waitlist claim links - monitor first real-world use | Cancel frees a seat -> the first waitlister is emailed a 24h claim link -> they claim it. Rehearsed as a full matrix on develop and shipped to prod; needs a read-only confirm on its first genuine use. | On the next real cancellation that frees a seat on a full, waitlisted event, confirm: notified_at/expires_at stamped, the email sent, the claimant claimed (member_rsvp with metadata source=waitlist_claim), and the waitlist row deleted. | Verify | Shipped 2026-07-19. Zero-cost proof on first real use, like the Remove & Refund WAIT-mode row.
BILLING-VIEWS ERA — ADDED 2026-08-03 · 12 items
Billing views: admin billing panel + member price/renewal display | Admin contact billing panel + member-facing price/renewal display. Three new profile columns (comp_reason, external_paid_through, external_payment_note) are live on both DBs; the UI/code build is in flight. | Extend admin contact detail with live Stripe billing; surface price/renewal/discount on member settings; wire the three new profile columns into admin editors. | IN PROGRESS | Columns live both DBs; code build in flight.
Report builder: admin/super_admin any-filter member/payment reports | Admin/super_admin reporting with arbitrary filters over members and payments. Data-cleanup prerequisite is DONE; build after billing views. | Build after billing views lands. Admin/super_admin only; any-filter member + payment reports. | QUEUED-BACKLOGGED | v1 proposal complete and approved-in-principle (DB-only cut, 3 entities, column picker, CSV export, 4 presets, server-paginated, ~7 files); resume at build sign-off. Cheap adds discussed: ambassador-referred, price tier, cancel reasons.
Business comp invite flow: welcome template + admin invite tool | Welcome email template plus an admin tool to invite a business member (comp path). | Blocked on Adam: invitee list + design answers. Then template + admin invite UI. | WAITING ON ADAM: list + design answers | Needs invitee list + design answers from Adam.
Admin 'Invite comp member' button - form (name, company, email, phone, comp note), creates comp'd account + sends welcome email, note auto-attached to billing view (member + admin); v1 invite flow built without UI, button is the addon | Admin UI button/form to invite a complimentary business member: name, company, email, phone, and comp note. Creates the comp'd account, sends the welcome email, and attaches the note to the billing view for both member and admin. | Addon after v1 invite flow (API/ops path without UI). Build the Invite comp member button + form once the headless invite path exists. | QUEUED | v1 invite flow built without UI; this button is the future addon.
Zane Mackey comp_reason entry | Record a one-phrase comp_reason on Zane Mackey's profile now that the column exists. | WAITING ON ADAM: one phrase for comp_reason. | WAITING ON ADAM: one phrase | One phrase for comp_reason.
Zach Trusky renewal ~Nov/Dec 2026 — honored $1,034 annual | Zach's annual amount lives outside Stripe ($1,034 honored). Need reminder + collection path decision around Nov/Dec 2026. | Schedule reminder; decide collection path (manual invoice vs Stripe annual vs override). | SCHEDULED NOV 2026 | Honored $1,034 annual; no Stripe customer today.
Security: unknown third-party script (batatatech.com) on Glue Up admin pages | Unknown batatatech.com script firing on Glue Up admin pages — treat as extension/malware until proven otherwise; audit browsers + rotate passwords. | Browser extension audit on machines that use Glue Up admin; password rotation for affected accounts. | OPEN - Adam chrome://extensions only | repo confirmed clean 8/4 - scope is Adam's chrome://extensions only
Calendar update-leg verification via throwaway event | Verify that event-edit REQUEST invites actually move real calendars (ICS sequence / update leg) using a throwaway event. | Create throwaway event, subscribe, edit, confirm calendars update; then delete throwaway. | OPEN | Throwaway event verification of REQUEST/update path.
Resend click-tracking subdomain (DNS) | Configure Resend click-tracking subdomain — Adam hands / DNS. | ADAM DNS: add Resend click-tracking subdomain CNAME + add Resend to SPF include (current SPF is Google-only). Confirmed missing 8/4. | ADAM - DNS | confirmed NOT configured 8/4; also add Resend to SPF include during same DNS visit
/welcome checkout-flow coverage on develop | /welcome checkout flow is still untested on develop (no Stripe checkout env there). | WATCH until develop has a Stripe checkout path; then cover /welcome end to end. | WATCH | Untested on develop; no Stripe checkout env.
Retire the Google Sheets tracker path | Repo xlsx under docs/ is the source of truth. Remove/deprecate update-backlog-sheet edge function, its secrets (BACKLOG_*, GOOGLE_SHEETS_SERVICE_ACCOUNT_JSON if unused elsewhere), and the delete/agent-auth additions. | QUEUED cleanup: delete the edge function (or stub 410), remove BACKLOG_AUTH_SECRET / BACKLOG_AGENT_SECRET / BACKLOG_SHEET_ID (and SA JSON if unused), scrub temp scripts. | QUEUED - cleanup | debug_env already stripped 2026-08-03; full retirement queued.
Admin card PATCH date normalization - external dates should save as noon UTC to avoid timezone off-by-one (Zach precedent) | external_paid_through saved as midnight UTC displays as prior calendar day in US Eastern (Zach showed Nov 30 instead of Dec 1). Admin billing PATCH should normalize date-only inputs to noon UTC. | In PATCH /api/admin/members/[id]/billing (and any similar writers), coerce external_paid_through date-only values to YYYY-MM-DDT12:00:00.000Z before save. SMALL. | OPEN | SMALL/OPEN. Precedent: Zach Trusky external_paid_through 2026-12-01T00:00:00Z → Nov 30 in America/New_York.
IDENTITY WAVES 0-6A + EXCHANGE ERA — ADDED 2026-08-24 · 9 items
Event editor silently reverts required_tier from the deprecated access dials on every save | AdminEventsTab loads the access dials from the deprecated columns (access_type_deprecated ?? access_type, line 713) and then re-derives the canonical required_tier from those dials on every save (lines 827-838 create, 890-901 edit). On any event whose deprecated dials disagree with its canonical required_tier, an unrelated save - a typo fix, a time change - silently reverts access. Confirmed root cause of the Exchange event flipping from public back to social between Aug 11 and Aug 13; it was corrected by hand through the admin UI on Aug 13 and will flip again on the next save. | Make required_tier the value the editor loads FROM, not a value re-derived from deprecated columns on write. Either load the dials from required_tier and dual-write the deprecated columns as the derived side, or drop the deprecated read entirely once the 11 remaining reader files are repointed. Until then, audit for events whose dials disagree with required_tier and reconcile them. Rehearse on develop - this touches every event save path. | Build | Root-caused 2026-08-13 during the Exchange flip-back hunt. High blast radius: any event whose dials disagree is one save away from a silent access change.
manifest.json declared but missing (site-wide 404) | src/app/layout.tsx:91 declares manifest: "/manifest.json" and middleware.ts:9 allow-lists the path, but no manifest.json exists in public/. Every page load requests it and gets a 404, so every public page carries a console error and the PWA install prompt never appears. | Add public/manifest.json with name, short_name, start_url, display, theme/background colours and the icon-192x192.png / icon-512x512.png already in public/. One file, no code change. Confirm the console is clean on / and /events afterwards. | Build | One-file fix. It is the only console error left on the public pages, so it masks real errors in every console assertion the rehearsals run.
Anonymous event page 401s (attendance count + host name) | Logged-out visitors on an event page get 401s on two reads: the attendance count and the host name lookup. Fallout from the Jul 9 lockdown that revoked anon on event_participants_view and dropped active_members - correct security, but the public page was never given a sanctioned path to the two harmless values it still displays, so both render empty. | Expose only those two values anonymously: a SECURITY DEFINER function returning a scalar attendance count for an event, and one returning a host display name (no email, no phone), both with anon EXECUTE. Do NOT re-grant anon on the underlying views. Verify from outside with the anon key that nothing else leaks. | Build | Console noise on every public event page today. Direct consequence of the (correct) Jul 9 anon-readable-view lockdown.
Localhost dev reads LIVE Stripe + Resend keys from .env.local | Local development loads .env.local, which carries production Stripe and Resend credentials. A checkout exercised locally hits live Stripe; a send path exercised locally hits live Resend against real member addresses. Nothing has fired by accident yet - the only thing preventing it is care. | Put TEST Stripe keys and a sandbox Resend key in .env.development.local, which Next loads ahead of .env.local for next dev while leaving production builds untouched. Then confirm a local checkout lands in the Stripe test dashboard and a local send reaches no real inbox. | Build | Raised during the Exchange develop rehearsals. Low effort, removes an entire class of accident. Pairs with the develop seed gaps row.
Develop seed gaps: no handle_new_user trigger, missing membership-card credential, fake sub_SEED003 | The develop database is not a faithful rehearsal surface in three ways. (1) The handle_new_user trigger that creates a profile on signup does not exist there, so signup behaves differently than prod. (2) The membership-card attendance credential that the wallet and door flows expect is missing from the seed. (3) A seeded subscription id (sub_SEED003) is not a real Stripe object, so any path that retrieves it from Stripe fails in a way prod never would. | Add all three to the develop seed: install handle_new_user on develop to match prod, seed the membership-card credential, and either create a real Stripe test subscription or make the seeded id obviously non-Stripe so code short-circuits instead of erroring. Re-run one signup, one door scan and one billing read on develop to confirm parity. | Build | Each gap has already cost rehearsal time by producing a develop-only failure that does not exist in prod. Closing them is what makes future rehearsals trustworthy.
comp-invite carries a local resolver replica (three copies of resolution logic) | comp-invite implements its own person-resolution logic instead of importing _shared/resolvePerson, so identity resolution now lives in three places: the shared resolver (15 adopters), the three Wave 3D database functions, and this local replica. Each copy drifts independently the next time the resolution rules change. | Repoint comp-invite onto _shared/resolvePerson and delete the replica. Do not modify the shared resolver to accommodate it; if the adoption is impossible without a resolver change, stop and report which prior adopters would need redeploy. | WATCH | Drift watch. Not wrong today, but it is the one edge function guaranteed to disagree with the other 15 after the next rule change.
Duplicate people rows labeled, merge adjudication deferred (Josh x3, Lance x3) | Two humans hold three people rows each. Josh: two canceled member rows plus a crystal.66 row. Lance: one active row plus two relics that hold zero attendance credentials and zero exchange_intake references. All six were labeled during the status pass; none were merged, because choosing the canonical row is a judgment call and Adam adjudicates fuzzies. | Adam picks the surviving row per human. Then merge additively: repoint references to the survivor and keep the losers as tombstones with metadata rather than deleting them. Re-confirm the two Lance relics still hold zero references immediately before any merge. | WAITING ON ADAM | Labeled during the Aug 19 status pass and deliberately left unmerged. Six rows, two humans. Folds naturally into the contacts fold (6B-6E). 2026-08-25: Josh's 4 hub_members rows were purged on the primary identity (a5f1b294) only; both duplicate rows held zero hub memberships, so that cleanup did not depend on this adjudication and does not constrain it.
Andrea Baquero past_due watch (invited Exchange registrant) | Andrea Baquero is past_due on billing and is also an invited registrant for the Aug 27 Exchange. If the past_due state persists, member gating could turn her away at a door she was personally invited to. | Watch through Aug 27. Either resolve the billing state before the event or confirm her Exchange credential is not tier-gated. Read-only until Adam decides how to handle the billing side. | WATCH | Time-boxed: this row closes after the Aug 27 Exchange, either resolved or converted into an ordinary billing follow-up. Aug 25: the 3+1 member_tier repairs done tonight included the tier-null row the payment-failure webhook re-created on this account Aug 24 — see the member_tier invariant row. The past_due watch itself still stands through Aug 27. Aug 26: RESOLVED to watch-only — billing email sent Aug 26; card in Stripe auto-retry; attends Aug 27 event; Adam reports ~2 attended events never captured at check-in.
Exchange v2 blueprint (mixer + intake, post-Aug-27) | Everything the dress rehearsal surfaced that did not justify building before the event: a reset control with a confirm guard; a standalone discard for a pending round (today only reshuffle exists, which replaces rather than discards); drag-a-person-between-tables; revisiting the 30-second minimum clamp on round duration (saveConfig floors it, so short demo rounds are impossible from the UI); a create-flow for setting up a mixer night from scratch; a partner-pool toggle; and answer-aware matching that seats people by their four intake answers rather than purely by repeat-pair avoidance. | Own detailed scope after Aug 27, informed by what actually happens on the night. Nothing here blocks v1. Sequence by what the night proves is missing, not by the order of this list. | Phase 2 | Compiled from the Aug 24 full-dress rehearsal. v1 shipped Aug 24 (viewer, mixer engine, board, UTM capture); the two findings worth fixing immediately - unseated visibility and the board email fallback - already shipped.
[P0] FINANCIAL TRUTH PROJECT + AUG 25 FINDINGS — ADDED 2026-08-25 · 8 items
[P0] Financial truth phase 1 — backfill the payment ledger from Stripe (all-time) | The database has never held a complete record of money received. 62 payment rows are confirmed missing, and the gap is not a single window: it spans the pre-app era (money collected before this application existed and therefore never written anywhere), the 5 subscribers who were never migrated into the app, and ordinary in-app payments the webhook dropped. Trinity French is the worked case study — $225 paid to Stripe, $0 of it in the ledger — and she is one of 62, not an exception. Every downstream number (MRR, churn, revenue by tier, the financial dashboard, any report built on payments) is computed from this incomplete table, so all of them are wrong by an unknown amount until the ledger is whole. | Backfill from Stripe as the source of truth, all-time, before touching anything downstream. Pull every charge / invoice / payment_intent from account creation forward, match to the person record through the unified resolver, and write the missing rows idempotently keyed on the Stripe object id so a re-run cannot double-post. Cover the three populations explicitly: pre-app-era payments, the 5 unmigrated subscribers, and the 62 confirmed misses. Reconcile the $809 of open invoices in the same pass — $645 is stranded on canceled subscriptions and should be voided, $170 is pre-app era, and only $114 is genuinely collectible. Rehearse the whole backfill on develop and diff the resulting totals against Stripe before running it against prod. | Build | Phase 1 of 4. Blocks phases 2-4 and every financial number in the product. Evidence: 62 confirmed missing payment rows; Trinity French $225 paid / $0 recorded; $809 open invoices ($645 to void on canceled subs, $170 pre-app era, $114 real). Backfill must be idempotent — it will be run more than once.
[P0] Financial truth phase 2 — fix the webhook silent-skip defect + add stripe_payment_intent_id | The Stripe webhook silently skips payments rather than failing loudly, which is why the ledger drifted without anyone noticing: a dropped payment produces no error, no alert and no row, so the only evidence is an absence nobody is looking for. The payments table also has no stripe_payment_intent_id column, so there is no durable key tying a stored row back to the Stripe object it came from — which makes both deduplication and reconciliation guesswork. | Two changes, both prerequisites for the reconciliation in phase 3. (1) Replace every silent skip in the webhook handler with a loud failure: log the Stripe event id, the reason, and alert — never return 200 on an unwritten payment. (2) Add stripe_payment_intent_id to the payments table with a unique index, populate it in the phase 1 backfill, and write it on every new payment. Prove the fix with a Stripe-CLI replay of the exact event shapes that were being skipped, on develop first. | Build | Phase 2 of 4. This is the defect that created the hole — fixing it stops the ledger re-diverging the moment phase 1 finishes. The new column is what phase 3 joins on. Aug 26: Requirement: journal invoice.voided (Stripe currently sole truth on voids, Rich case Aug 26).
[P0] Financial truth phase 3 — nightly two-way reconciliation with loud mismatch alerts | Once the ledger is whole (phase 1) and the webhook stops dropping rows (phase 2), the remaining risk is silent drift: any future gap between Stripe and the database is invisible until someone audits by hand, which is exactly how 62 rows accumulated. Nothing today compares the two systems on a schedule. | Scheduled nightly job that reconciles in BOTH directions — every Stripe payment must exist in the ledger, and every ledger row must exist in Stripe — joined on stripe_payment_intent_id. Any mismatch alerts loudly (not a log line nobody reads) with the offending ids attached, and surfaces on the admin health dashboard alongside the cron / webhook widgets. Pairs with the Q6 canceled-drift tripwire and the DB/Stripe drift watch rows; consider folding them into one money-drift check rather than three. | Build | Phase 3 of 4. Turns 'the numbers are right tonight' into 'the numbers stay right'. Depends on the stripe_payment_intent_id column from phase 2.
[P0] Financial truth phase 4 — rebuild the financial dashboard on the clean ledger | The financial dashboard was built in Lovable on the incomplete payments table and has never been trusted (churn once displayed 2055%). Rebuilding it before the ledger is whole would only re-derive wrong numbers from a wrong source, so it is deliberately sequenced last. | After phases 1-3 land, rebuild MRR, churn and revenue-by-tier directly on the reconciled ledger, then verify each figure against Stripe by hand once before trusting it. Absorbs the existing 'verify the financial dashboard' and 'verify the admin financial data function' rows, and is where the three-bucket collected / projected / churned view should land. | Build | Phase 4 of 4. Do NOT start before phase 1 completes — a dashboard on a partial ledger is the current problem, rebuilt. Supersedes the older FINANCIALS verify rows.
member_tier invariant hole: an active member can hold a null tier, and the webhook re-creates them | Nothing in the schema forbids the broken state. There is no CHECK constraint and no default preventing an active member from having a null member_tier, the partner member type has no tier mapping at all (so partners are structurally tier-null), and the payment-failure webhook re-creates tier-null rows even after they have been repaired by hand — Andrea's Aug 24 case is the proof that manual repair alone does not hold. Anything that gates on tier (event access, portal views, pricing) behaves unpredictably against a null. | Close the hole at the database level rather than by repeated repair. Decide the correct tier for the partner type first (it needs a real mapping, not a null), then add a CHECK constraint or default that makes 'active with null tier' unrepresentable, and fix the payment-failure webhook path so it preserves the existing tier instead of writing a row without one. Repair the outstanding rows in the same pass and re-check after the next real payment failure. Follow the incremental CHECK-constraint approach already agreed on the enums row — one table, carefully, not a schema-wide sweep. | Build | Aug 25: the 3+1 tier repairs were done tonight, but they are repairs, not a fix — the webhook will re-create tier-null rows until the write path and the constraint both change. Partner-type mapping is the open decision inside this row. Verified end state 2026-08-25: Jacob Cohen, JD Davis and Vaishali Willis all read member_tier 'social'; Andrea Baquero's row reads social too (updated 20:19:51 UTC) but she is still past_due, so the Stripe retry did not clear the money. 13 people rows holding a member role still carry a null tier, and exactly ONE of those is active - partnertest@704collective.com - which is the partner-type mapping hole above rather than a missed repair. ~20 people rows carry member role with null status; partnertest maps to no tier; normalize during invariant fix.
hubs.created_by is NOT NULL ON DELETE CASCADE — deleting a creator profile destroys their hubs | The hubs.created_by foreign key is NOT NULL with ON DELETE CASCADE, so hard-deleting a profile deletes every hub that person created and everything those hubs contain. This is a live footgun on any exit or cleanup workstream: an ordinary-looking profile delete silently takes member-facing content with it, and there is nothing in the admin UI that warns about it. | Change the cascade to something survivable: make created_by nullable with ON DELETE SET NULL, or repoint deleted creators to an organisation-owned system account, so hubs outlive the person who made them. Until that lands, treat any profile hard-delete as a two-step operation — audit owned content first (the read-first footprint audit already used on member removals), reassign or purge deliberately, then delete. | Build | Aug 25: surfaced during the Josh hub-membership cleanup forensics, not because Josh owned anything - he created zero hubs. All four hubs (The Arrival, Business Founders, Eats & Experiences, The Wellness) are created_by Adam, so the whole Network content structure hangs off one profile row and that is where the exposure sits. Soft deletes are safe; the hard-delete path (admin-delete-user, manual profile delete) is the footgun. Same class as the bulk-delete atomicity row.
Retention watch: 7 members exiting by Sep 13 — $287/mo MRR at risk | Seven members are on track to exit by Sep 13, representing $287 per month of recurring revenue. Recorded as a dated watch so the number is tracked deliberately rather than discovered in a month-end total. | Track through Sep 13. Decide per member whether anything is worth doing (conversation, offer, pause instead of cancel) before the exits land, and confirm the actual outcome against this figure afterwards. Feeds the member-cancellation retention flow row — that build should be scoped by what these seven actually say. | WATCH | Time-boxed: this row closes after Sep 13, either as a recorded loss or as retained members. $287/mo across 7 members. Note the financial figures here come from Stripe, not from the ledger the financial-truth project is fixing.
Members-by-type admin view — spec discussion in progress, build pending Adam's five answers | An admin view of members broken out by type. The spec conversation with Adam is underway but not finished: five questions remain open, and the build is deliberately not started until they are answered, so that the view is built once against a settled definition rather than reworked. | Finish the spec discussion with Adam and capture the five answers here, then build. Reuse the canonical person record and the existing member-type vocabulary rather than inventing a parallel definition — the same classification that the member_counts view and the directory work already use. | WAITING ON ADAM: five answers | Spec in progress as of Aug 25. Build is intentionally blocked, not forgotten. Related to the unified admin users view and the member directory rows.
AUG 26 FINDINGS — ADDED 2026-08-26 · 4 items
Attendance undercount is systemic — door discipline, not a data bug | Attendance is only ever as true as the door. Adam reports roughly two events Andrea Baquero attended that were never captured at check-in, and the same gap exists for anyone scanned inconsistently. This is not a reporting defect: the records are never written at all, so every downstream number that rests on attendance is quietly low and nothing signals it. It is event-critical for the Exchange specifically, because the mixer roster is built from check-ins — an uncaptured arrival is a person the engine will never seat. | Treat as an operations fix first, not a code fix. Add an explicit check-in line to the run-of-show for the Aug 27 Exchange so every arrival is scanned or recorded by hand, then measure that night's capture against the known headcount. Only if capture is still short does this become an instrumentation problem in the door path. Backfilling historical attendance is a separate decision, and not worth making until live capture is trustworthy. | Build | Raised Aug 26 from the Andrea Baquero case (~2 attended events never captured). Immediate lever is the Aug 27 run-of-show line.
Hub add-member search still surfaces banned business members | The add-member search on /admin/hubs was narrowed Aug 26 to active business members with is_internal false, but banned was deliberately left out of the filter set. A banned business member with an active subscription therefore still appears in the search and can still be added to a hub. The member-facing hub tab hides them correctly, so the effect is an invisible member occupying a row rather than a data leak. | One line in the add-member search query: .eq('banned', false), alongside the existing deleted_at, member_type and is_internal filters. Same rehearsal shape as the Aug 26 hub work — seed a banned business member, confirm it is absent from the search, and confirm the member-facing tab is unchanged. | WAITING ON ADAM | Left open on purpose Aug 26: the shipped scope named member_type and is_internal only, so the gap was reported rather than silently widened. One-line change whenever Adam approves.
Email logo still partially inverts in Gmail dark mode | The member blast logo was changed Aug 26 from the white-on-dark mark to the circular badge on an opaque white circle. That fixed the logo disappearing entirely and was render-verified for contrast in both light and dark-emulated views. In real Gmail, dark-mode inversion still partially affects the surrounding shell, so the badge is legible but the treatment is an improvement rather than a complete answer. | Next lever is a dark-mode-aware CSS asset: prefers-color-scheme rules plus explicit background locks on the shell, and where Gmail ignores those, a pre-composited image asset that cannot be inverted. Verify against a real Gmail dark-mode client, not only an emulated render — the emulated view is what passed while the real client still differed. | Build | Badge shipped Aug 26 and is legible; this row covers the remaining shell inversion. Cosmetic and low urgency, but it touches every member-facing send.
Sentry: "load" error thrown on /dashboard (~Aug 24), undiagnosed | Sentry reports an error on the member dashboard in which a Supabase error object appears to be thrown rather than handled, surfacing with the message "load". It first appears around Aug 24. Nothing else is known — frequency, affected users, and whether the page actually degrades are all unread, because the issue detail has not been opened. | Blocked on evidence, not on effort. Adam sends the Sentry issue-detail screenshot (stack, breadcrumbs, event count, affected users) and diagnosis follows from there. Likely shape is an unchecked Supabase call whose error object is thrown as-is, which is why the message reads as the object rather than a cause — but that is a guess until the throw site is visible. | WAITING ON ADAM: issue-detail screenshot | Raised Aug 26. Cannot be triaged from the title alone; the throw site is what identifies it. First seen ~Aug 24.
OCT 21 — HUB LAUNCH / LEADS — PARKED, NOT LOCKED · 7 items
Lead emails: proposal = business + copy to hello@. Need lead emails from Larry, CAF, Jon, Antonio. Confirm which emails fire per lead today. | Parked with hub launch. Not locked. |  | PARKED
CAF: waiting on their shared lead inbox; check if one listing can have 3 logins. | Parked with hub launch. Not locked. |  | PARKED
2-day reply nudge: proposal = on at launch; Adam tells businesses the reply expectation first. | Parked with hub launch. Not locked. |  | PARKED
Moving-to-Charlotte funnel: separate cltbucketlist.com build after hub launch; dual CLTBucketlist + 704 partners only (CAF, Larry); listing fee TBD; decide if Zach/Tyler become dual partners; Ascent content never routes to CAF. | Parked with hub launch. Not locked. |  | PARKED
Tyler (Gold Medal Wealth / NM): compliance answer pending. | Parked with hub launch. Not locked. |  | PARKED
Roster replies pending: CAF, Zach, Tyler, Larry, Jon, Antonio. Headshots on hand: Zach, Antonio, Tyler. | Parked with hub launch. Not locked. |  | PARKED
After hub launch: re-submit sitemap in Google Search Console + Bing. | Parked with hub launch. Not locked. |  | PARKED
OCT 21 — OTHER OPEN · 6 items
Door check-in: build the server-side lock BEFORE any host/volunteer gets an admin login. | Must land before any host or volunteer admin login. |  | Build
Ambassadors: 4 have unfinished Stripe setup (1 rejected by Stripe) — decide on a nudge email. | Decision only. No email until Adam says so. |  | OPEN
Wallet pass scan: real test at the door (Putt Putt Oct 22). | Real-device scan at the door. |  | Verify | Putt Putt Oct 22
Optional: real "Sign in with Google" test with a non-member Google account. | Optional live test. |  | Optional
Optional: React #418 on mobile home — watch only (not reproducible). | Watch only. Not reproducible. |  | Watch
Cosmetic, later: stripe-webhook should clear canceled_at on reactivation (bundle with next webhook change). | Do not touch stripe-webhook until the next webhook change. |  | Later