## Tracker
Item | What it is / why it matters | Build guidance | Status | Notes
ONBOARDING & SIGNUP · 2 items
Collect phone for everyone at signup; gate texts on consent | Phone is captured at signup now; the remaining work is gating SMS on the consent flag (not on whether a number exists) and re-collecting phone from pre-May-21 members whose number was never saved. | Confirm phone persists from signup metadata; gate SMS on the consent flag; add a re-collection prompt for pre-May-21 members. | In Progress | Phone capture + display already shipped; consent gate + backfill remain.
Prompt calendar-subscribe + wallet-pass add at signup | As part of signup, walk the new member through subscribing to the event calendar and adding their wallet pass, so both are set up before they finish onboarding. | Add a calendar-subscribe step and a wallet-add step to the signup / onboarding flow; confirm both stick. | Build | New onboarding-flow ask — pairs with the lifecycle push to current members (see Email & Drip).
MEMBERS & MONEY · 3 items
Verify the payment-to-membership chain end to end | The full money path (checkout -> Stripe webhook -> member activated) has no automated test. | Run a Stripe-CLI end-to-end test of checkout -> webhook -> activation before scaling referrals on it. | Verify | The money path — verify carefully; everything downstream assumes it works.
Verify an email change keeps Stripe billing in sync | When a member changes email, the Stripe customer should update too, so billing/receipts don't split into a second identity. | Change an email; confirm the Stripe customer email updates; no orphaned customer. | Verify | Prevents a second, orphaned Stripe identity on email change.
Migrate the 8 legacy $30 subscriptions | The trusted member-count definitions are already established (member_counts view). The only residual is 8 subscriptions still on the retired $30 price. | Move the 8 legacy $30 subs to current pricing in Stripe; $30 is retired everywhere else. | Build | Count reconciliation itself is DONE — this is the leftover cleanup.
IDENTITY FOUNDATION · 3 items
Merge every person into ONE record with a real login ID | The same human exists across profiles/people/contacts, glued by matching email text — the root cause of recurring identity bugs (9 paying members recently couldn't RSVP). Locked: one canonical person keyed by a permanent auth_user_id. | Add auth_user_id -> repoint reads -> repoint writes -> auth-adjacent last, in waves. One resolver everywhere. Regression-test logins + RLS from a non-admin session before cutover, behind a verified backup/rollback. Member type stays a STATUS on the person. | Build | The foundation most other work depends on; ~55 files to repoint. Do it live in waves, never a big-bang switch.
Finish the unified RSVP recipient resolver | One reliable 'who is this RSVP for' that every surface uses. | Build the single recipient resolver on the canonical person record; replaces per-surface lookups. | Build | Unblocks scaling ambassador signups.
Finish retiring the old ticket tables | RSVP moved to one attendance table; a guest-pass follow-up tracker and one hook still dual-write the old 'tickets' table. | Repoint last guest-pass readers/writers to attendance_credentials, kill the dual-write, drop legacy tickets + guest_passes after a safe soak. | Build | Don't drop before the soak confirms nothing else reads them.
EVENTS & CALENDAR · 19 items
Require an event category at creation | Every event needs a category label at creation (a mis-filed event was shown to the wrong audience). Category is separate from access level. | Two independent fields on the event form — Category (editable label) and Access level — both enforced at creation. | Build | Categories: The 704 / The Reserve / After Hours / The Reset / For the City / The Exchange / Coffee & Connect.
Three event access levels: open / members / business | Production already runs business-only events; the old two-bucket spec needs three: open to all, members only, business-members only. | Implement a 3-value access field driving visibility + RSVP eligibility. | Build | Drives both event visibility and who can RSVP.
One simple event feed everyone sees | Locked: no separate social vs business feeds for now; one feed shows everyone all events. | Ship the single simplest feed; access level still governs RSVP eligibility. | Build | Single feed for now; tiered feeds are explicitly deferred.
Confirm the 118 old calendar links work again | When the feed broke, ~118 members held subscribe-links returning an empty calendar; the June 10 rebuild likely revived them. | Spot-check several of the 118 tokens against the live feed; if events return, close it — else send a re-subscribe email. | Verify | Likely already revived by the June 10 rebuild — confirm, then a soft 'your calendar works' note at most.
Alert if the calendar feed ever goes empty again | The feed broke silently last time. | Cron/health-check comparing feed output to known future events; alert on mismatch. | Build | Catches a silent feed failure like the earlier one.
Verify the event detail page handles every state | Member + public RSVP are verified; waitlist, paid purchase, capacity-full, and cancel/re-RSVP are not. | Test the remaining EventDetail branches. | Verify | Core states already verified; this covers the edge branches.
Verify the RSVP status sidebar shows the right state | Confirm the sidebar reflects all 7 RSVP states. | Walk all 7 states: not RSVP'd, RSVP'd, waitlisted, cancelled, attended, refunded, no-show. | Verify | Purely a verification walk-through; not a build.
Show non-members a teaser of members-only events | A non-member should see members-only events as a teaser: type + 'Members Only' tag, never the location. Creates FOMO, sells membership. | Public view: type + tag, hide name details, always hide location. | Build | Awaiting a fuller public-events-page spec before final build.
Verify the remaining door check-in scan paths | Member check-in is verified; walk-in (no-RSVP) record, guest-pass scan, and junk-scan rejection are not. | Test walk-in QR, guest-pass (GP-) scan, and gibberish-scan rejection. | Verify | Member check-in already verified; this covers walk-in, guest-pass, and bad scans.
Hide all event details until someone RSVPs | By default, all event details are hidden from everyone (even in the portal) except photo, preview name, and date/time; full details reveal only after RSVP. | Default-hide name/location/details; reveal post-RSVP; controlled from the event manager. | Build | Build after the core events work is stable.
Polite no-show email | When a member RSVPs but doesn't show (known from check-in), send a kind 'only RSVP if you can attend' email — resources are planned around counts. | Trigger off check-in data (RSVP'd + not scanned = no-show). | Build | Depends on stricter RSVP + solid check-in data.
Persist public RSVP confirmation + on-page QR | When a non-member RSVPs, keep them confirmed on reload and show their QR on the confirmation page (+ email); no account required. | Persist confirmed state on reload; render QR on the confirmation page + email. | Build | No account creation for the public RSVP — just persistence + QR.
Optional event host (name + photo) | Let an event optionally show a host with name and photo. | Event host field + admin form + display. | Build | Simple optional field; no dependencies.
Future-event visibility limits | Define and enforce how far ahead events are visible (date range, tier, or capacity). | Scope the limit dimension, then enforce. | Build | Decide the limit dimension before enforcing.
Soft-delete for events | Let events be recoverable rather than hard-deleted. | Soft-delete events. | Build | Related to the event-DELETE RLS failure that the identity fix resolves.
Self-serve event management | Let hosts/business members propose or manage their own events (admins publish). | Define permissions — likely 'propose -> admin publish'. | Build | Needs scoping before build.
Event reorganization | Restructure how events are displayed per the events direction. | Needs the detailed events-page spec. | Build | Blocked on the detailed events-page spec.
Calendar scope picker in settings | Optional: let business members narrow their calendar to business-only. | Implement only if tiered feeds return. | Build | Optional given the single-feed decision; only relevant if tiered feeds return.
Instant Google Calendar updates | Subscribed calendars refresh every 8-24h; true instant needs a Google Calendar API push integration. | Service account writing to each member's calendar. | Build | Larger effort — a Google Calendar API push integration.
WALLET PASS · 5 items
Verify Apple Wallet passes work on real phones | Confirm generate, deliver (dashboard + email), and update-on-status-change end to end; code is further along than expected. | Test on a real iPhone; fix gaps. | Verify | Generation + push-update already exist — verify on a real device, then close gaps.
Kill a membership pass when someone cancels | When membership lapses/cancels, the pass must stop scanning at the door; a void function exists. | Verify cancellation voids the pass and it dies on-device. | Verify | Nothing should scan at the door after membership ends.
Give members a QR backup if their pass fails | Door failure modes: dead battery, no signal, deleted pass. | Dashboard QR fallback + 'resend my pass' button. | Build | Assume bad connectivity at the door.
Complete Google Wallet passes | Bring Google Wallet to parity with Apple (generate/deliver/update); the scaffold is partial. | Finish Google Wallet generation + delivery + update. | Build | Scaffold is partial; bring to parity with Apple.
Apple Wallet push notifications + email attachment | Push on changes + pass-as-email-attachment. | APNs push + email attachment. | Build | After pass voiding is working.
AMBASSADORS · 8 items
Finish and test the full ambassador referral + payout system | Locked Phase 1. Core attribution bug half-fixed: referral-writes failed silently on wrong column names (17 ambassadors / 0 logged); the column fix is live but not yet confirmed writing a real row. | Verify the column fix writes one real referral; fix business-tier stamping in create-checkout; build payout rails + manual queue; wire the second-payment commission; then strip the diagnostic logs. | Needs Testing | Commission counts on the member's SECOND payment (locked). Diagnostic logs left as the witness — remove only after confirmed writing.
Verify the referral price applies at checkout | Confirm the $35 ambassador-referred social price applies via a referral link (vs $49). | Confirm referral checkout shows $35. | Verify | Checks the $35 referral price vs the standard $49.
Build the ambassador payout infrastructure | The money-movement side of payouts (Stripe Connect Express or a manual queue). | Build payout rails; decide Connect vs manual queue. | Build | Pairs with the referral-fix row.
Build the manual payout queue UI | An admin UI to review and release ambassador payouts. | Payout queue UI for admins. | Build | Where an admin reviews and releases payouts.
Weekly automated ambassador payouts | Scheduled automatic payouts once the rails exist. | pg_cron weekly payout run. | Build | After the payout infrastructure exists.
Ambassador leaderboard | A leaderboard ranking ambassadors by referrals. | Ambassador leaderboard. | Build | Ranks ambassadors by referrals.
Read-only ambassador tab | A view-only tab for ambassadors to see their own referral activity. | View-only ambassador tab. | Build | Ambassadors see only their own activity.
Unified admin users view (members + ambassadors) | One admin view combining members and ambassadors. | /admin/users unified view. | Build | Combines members + ambassadors in one admin view.
MEMBER TEXTING · 2 items
Confirm we're cleared to send texts (Twilio A2P 10DLC) | Records conflict on whether A2P 10DLC is approved; one call to Twilio settles it. Gates all texting. | Confirm A2P 10DLC status directly with Twilio; assign an owner + date. | Blocker | Nothing SMS ships until this is confirmed.
Build the portal-baked texting inbox (Charlotte number, shared, consent + STOP) | All member texting runs through ONE Charlotte-based Twilio number wired into the admin portal — no managed third-party tool, and no text ever reaches a personal phone. Inbound messages hit a webhook, write to our database, and appear in a shared team inbox where every co-founder can read and reply; replies send from the club number. Consent and STOP are enforced and stored on the canonical person record. | Twilio number -> inbound webhook (Edge Function) -> DB -> portal Messages inbox (threads per member) -> reply sends from the club number. Enforce consent + instant STOP; log idempotently before send; dedup in one shared send function. Inbound triggers an alert (email + the in-portal notification bell). Standard outbound: welcome, Monday digest, day-before reminders, week-1/2 nudges. Layer 1 only — no AI agent. Burn in 5-7 days. | Build | HARD REQUIREMENT: nothing lands on a personal cell; fully transparent + team-managed. Gated on the A2P confirmation, the phone-storage model, and the identity foundation.
SECURITY · 3 items
Rotate the shared admin password before the developer starts | The super-admin password was shared in working sessions; rotate it before any third-party developer gets repo/dashboard access. | Rotate super-admin + test-account credentials before granting access (~10 min). | Blocker | Owner task — a prerequisite before onboarding the developer.
Rotate and remove secrets committed to the code | Live GroupMe join tokens were committed to git history; the file was deleted but the tokens stay readable until rotated. | Rotate the exposed tokens (rotate-only, no history rewrite). | Blocker | Rotate so the committed copies become useless; no history rewrite.
Run a database security + linter pass | A sweep for DB security issues and schema problems before scaling. | Run the DB linter + security audit; fix findings. | Build | Also re-confirm the already-shipped public-checkout auth fix here — don't redo it.
SECURITY & MONITORING · 4 items
Turn on error monitoring (Sentry) | Sentry is installed but never switched on, with no server-side capture; until it's on, no fix is provably working in production. | Initialize across client + server + API routes + a root ErrorBoundary. Company-owned. | Build | Until it's on, no fix is provable in production — it's the verification backbone.
Add a deploy pipeline so changes go live safely | DB/function changes are pushed by hand today — the root cause of code/live drift. Locked: hand-patching stops once this lands (with a written emergency lane). | GitHub Actions: merge to main -> db push + functions deploy. Needs 3 repo secrets. | Build | Once in, hand-patching stops; needed before two people touch production in parallel.
Make the code able to rebuild the live database | Several live DB objects were made by hand and aren't in migration history, so the repo can't recreate prod. | Snapshot prod schema, diff vs migrations, commit a baseline migration. | Build | Absorbs recent hand-made objects (RSVP backfill, a few functions, the unsubscribe function).
Add three safety tests on the things that can't break | Effectively no automated testing exists. | Three critical-path tests — (1) checkout -> webhook -> activated, (2) RSVP -> attendance, (3) unsubscribe honored — and remove passWithNoTests so CI gates. | Build | The three failures that hurt most; flips CI from passing with zero tests.
EMAIL & COMPLIANCE · 2 items
Make every email sender respect unsubscribes | The unsubscribe page/link policy is fixed, but two senders (drip processor, renewal reminders) still don't check the opt-out flag, and one reminder may skip members on a null value. | Add opt-out filtering to process-drips + renewal-reminders; fix event-reminder null handling. One opt-out flag is the source of truth. | In Progress | send-email unsubscribe-block work is in flight; process-drips + renewal-reminders filtering to confirm/finish.
Make unsubscribe links forgery-proof | The unsubscribe token is currently guessable/forgeable (low stakes). | HMAC-sign the token; align format across send-campaign, send-email, and unsubscribe. | Build | Align the token format across the three places that generate/read it.
ADMIN & OPERATIONS · 10 items
Add a private notes section on each member | Internal request: a notes area per member for context (e.g. 'comped through August'). | Read: admin + super-admin. Write/edit: super-admin only. Not member-visible. | Build | Internal-only; super-admin writes, admins read, members never see it.
Build the admin health dashboard | One screen showing system health at a glance; catches silent failures before members do. | 5 widgets — cron, webhooks, drip health, email tracking, payment sync. Sits on /api/health. | Build | Reads /api/health + checks; surfaces silent failures.
Let admins change a member's tier and have billing follow | App-side tier change/comp exists; the Stripe billing side doesn't follow. | Wire admin tier-change to Stripe subscription cancel/modify/start. | Build | App-side override already exists; this is the Stripe billing reconciliation.
Harden the admin cancel-subscription flow | Make admin cancel safe (running twice shouldn't double-act). | Add idempotency + structured logging + alert to admin-cancel-subscription. | Build | Idempotent + logged + alerted so a double-run can't double-act.
Build the admin area into clean sections | Reorganize admin into Today / People / Events / Network / Money / Messages / Settings with one source of truth per question. | 7-section IA; folds in nav cleanup, per-event check-in start, financial accuracy, tier tools, and guest upload. | Build | The Messages section is where the texting inbox lives.
Shared admin navigation config | One shared config for admin nav so it's consistent and not duplicated. | Single adminNav config; remove duplicated nav definitions. | Build | One config; removes duplicated nav definitions.
Guest list upload tool | Let admins upload a guest list for an event. | Guest list upload UI. | Build | Also unblocks future guest-conversion automation.
Fix the organization settings table | organization_settings has the wrong schema. | Correct the organization_settings schema. | Build | Schema is currently wrong; correct it.
Route Stripe receipts to the team inbox | Receipt/invoice emails should also go to hello@704collective.com. | Stripe email settings -> CC hello@ (or a forwarding rule). | Build | CC hello@ on Stripe receipts, or add a forwarding rule.
Restore attendee click-through for guests | In the admin attendee list, public/guest rows aren't clickable (only member rows route). | Bridge people -> contacts so guest/public rows are clickable. | Build | Cosmetic; bridge people -> contacts so guest rows route.
MEMBER EXPERIENCE · 9 items
Strip member profiles to four clean fields | Simplify the profile to name, photo, what you do, and a one-line bio — as real columns, not JSON. Locked: archive the other 15+ fields (kept in DB, hidden) for future matchmaking. | 4 visible fields as real columns; align onboarding + settings + directory. The 4-field data move rides with the identity foundation (same plumbing). | Build | Archive (don't delete) the rest — raw material for future matchmaking.
Build the one merged member portal with tiered views | Locked: replace the two portals (member dashboard + business portal) with ONE codebase; business gets an elevated view, social the standard view; clear type distinction preserved. | One portal codebase; gate business-only modules behind member type. Replaces /dashboard vs /business-portal. | Build | Replaces /dashboard vs /business-portal with one tier-gated codebase.
Rebuild onboarding questionnaire + member brief | Store responses in their own table and generate a 'member brief' for future matchmaking/AI. | Onboarding rebuild + onboarding_responses table + member_brief column. | Build | Responses in their own table; feeds a future member brief.
Member portal / dashboard redesign | The redesign: 5-tab bottom nav, pass-first / next-event hero, onboarding checklist removed after completion, plus resources/bookings tabs. The shared activity feed is KEPT and built on (members post / share / like; event discussions surface there) — only the minor personal activity-log widget from the old dashboard is retired. | Multi-week. SEQUENCING: the visual redesign lands AFTER the identity foundation is built and verified — not concurrent with it (one big change at a time on a no-staging system). Resources/bookings depend on vendor partnerships. | Build | Activity feed stays; only the personal activity-log widget is retired. Visual redesign sequenced after identity.
Member directory — people-finder for all member + partner types | A members-only people-finder where social members, business members, and partners can all find and see each other — profiles only, WITHOUT the business-listings view. Visible to everyone logged in, regardless of type. A privacy toggle lets a member hide from it. | Logged-in directory of people (social + business + partner). Profiles only — no business view (that lives in The Network). Visible to all logged-in types; honor the privacy toggle. | Build | Distinct from The Network (hubs + business/partner listings). Pairs with the privacy toggle below.
Profile privacy toggle | A toggle for members to control whether they appear in the directory and the internal Network member view. | Build the opt-out toggle; default is listed, members can hide themselves. | Build | Confirmed feature — the directory is opt-out via this toggle.
Member cancellation retention flow | Improve the cancellation flow with retention UX. | Retention UX on cancellation (offers, pauses, feedback). | Build | Offers / pauses / feedback on cancellation.
Member spotlight on calendar/home | Feature a member spotlight on the calendar/home pages. | Member spotlight feature. | Build | Feature a member on calendar/home.
Unlimited guest passes for dream-team members | An override flag letting select members bypass the monthly guest-pass cap. | Override flag bypassing the guest-pass cap. | Build | Override flag for select members.
PERFORMANCE · 5 items
Speed up slow list pages (Events, Tasks, Hubs) | These pages make many small repeated DB calls (N+1) that get slow as data grows. | Resolve the N+1 query patterns; batch them. | Build | Batch the repeated calls on Events, Tasks, Hubs.
Make bulk member adds all-or-nothing | Bulk add isn't transactional — a partial failure leaves half-written data. | Make add-members and hub-delete atomic. | Build | All-or-nothing; same for hub deletes.
Move heavy admin queries to the server | Keep the browser from doing heavy lifting on admin overview + email dashboard. | Add server-side RPCs: admin_overview, email_dashboard. | Build | Move admin overview + email dashboard to server RPCs.
Standardize how data is loaded (React Query) | Make loading behavior uniform and reliable. | React Query rollout across data fetching. | Build | Uniform data-loading / caching across the app.
Audit shortcut data fields for correctness | Some proxy fields stand in for real data and may be stale. | Proxy field audit. | Build | Some stand-in fields may be stale; audit them.
AUTH · 5 items
Verify magic-link login across two devices | Phone-to-desktop: request a link on a phone, type the 8-digit code on the desktop. | Cross-device OTP test; confirm same-device + resend cooldown too. | Verify | Requires a second device (owner-run).
Verify magic-link login works in production | End-to-end check the email magic-link round-trip works live. | Test request -> click -> signed in, in prod. | Verify | End-to-end live round-trip check.
Verify sessions refresh correctly on expiry | Confirm cookie-based refresh works when a token expires so members aren't kicked out. | Verify @supabase/ssr middleware refreshes session on token expiry. | Verify | Confirm members aren't kicked out when a token expires.
Verify Google sign-in works | Confirm Google login/signup paths work in production. | Test Google OAuth signup + sign-in. | Verify | Confirm Google login/signup in production.
Apple Sign-In | Add Apple Sign-In as a login option. | Apple Sign-In. | Build | Add as a login option.
BUSINESS · 1 item
Verify the business application approval works | Confirm the edge function that approves business applications works as intended. | Verify approve-business-application end to end. | Verify | Confirm approve-business-application works end to end.
FINANCIALS · 6 items
Verify the financial dashboard | Confirm it reports MRR, churn, and revenue by tier correctly (churn once showed 2055%). | Verify financial dashboard accuracy. | Verify | Built in Lovable originally — accuracy unconfirmed.
Verify the admin financial data function | Confirm the edge function feeding admin financials returns correct numbers. | Verify admin-financial-data. | Verify | Confirm the numbers it returns are correct.
Three-bucket revenue view | Show revenue split three ways. | Collected / projected / churned split. | Build | Collected / projected / churned.
Member-facing financial widget | A small financial widget members can see. | Member-facing billing-status widget. | Build | Small billing-status widget for members.
Reduce redundant Stripe scans | Cut how often the system scans Stripe, for performance/cost. | Reduce Stripe API scan frequency. | Build | Cut scan frequency for cost / performance.
Past-due dismissal flow | A flow to dismiss/handle past-due payment states cleanly. | Past-due handling/dismissal. | Build | Handle / dismiss past-due states cleanly.
EMAIL & DRIP · 13 items
Drip email health banner | A banner flagging when drips are silently failing or stalled. | Drip health-check banner. | Build | Flags silently failing / stalled drips.
Guest follow-up drip (7 + 20 day) | Automatic emails to guests at day 7 and 20 to convert them. | Guest 7-day + 20-day drip. | Build | Converts guests at day 7 and 20.
14-day RSVP prompt for new members | Nudge new members who haven't RSVP'd within 14 days. | 14-day RSVP prompt drip. | Build | Nudges new members who haven't RSVP'd.
Confirm the email log matches actual sends | Today failures are swallowed; make 'did this send' provable. | email_log row matching; stop swallowing failures. | Build | Stop swallowing failures so 'did this send' is provable.
Per-email open/click analytics | Track opens/clicks per template so we know what works. | Per-template email analytics. | Build | Per-template open / click tracking.
Per-member engagement scoring | Score each member's engagement from email/event activity. | Engagement scoring per member. | Build | Score members from email / event activity.
Category-level unsubscribe preferences | Let members opt out of specific categories, not all-or-nothing; builds on the one-flag fix. | Per-category opt-out prefs + a member settings page. | Build | Builds on the one-flag opt-out fix.
Branching drips based on opens/clicks | Drip sequences that branch on open/click. | Open/click-branching drips. | Build | Branch sequences on open / click.
Send email from a contact record | Let an admin email directly from a member/contact record. | Send-email action on the contact record. | Build | Admin emails directly from a member record.
Attachments and images on event email campaigns | Let campaign emails include attachments and images. | Extend the campaign editor for attachments + images. | Build | Extend the campaign editor.
Live test the guest-pass drip | Confirm the drip fires correctly on a guest pass. | Live test the drip on guest_pass. | Verify | Confirm it fires on a guest pass.
Merge guest follow-up into the drip processor | Retire the separate guest-followup function and fold it into the main processor. | Consolidate guest-followup into process-drips. | Build | Fold guest-followup into process-drips.
Push current members to subscribe to the calendar + add their pass | A proactive email and in-portal prompt to existing members to (re)subscribe to the event calendar and add their wallet pass — absorbs the 118 dead-calendar-link re-subscribe into one general push. | Campaign + in-portal prompt to current members: (re)subscribe to the calendar and add the wallet pass. Covers the 118 dead links. | Build | New lifecycle ask. Sending email is a money/send action — gate it and verify before sending.
DATA & CLEANUP · 6 items
Add last-attended tracking | No 'last attended' field today; unblocks inactivity tracking + retention. | last_attended column + trigger. | Build | Unblocks inactivity tracking + retention.
Status fields as proper enums | Replace loose text status fields with enums to prevent typos/bad states. | Convert status strings to enums. | Build | Prevents typos / bad states from loose text.
RSVP attribution by event ID | Tag RSVPs/contacts by event ID, not a slugified title (which breaks on rename). | contact_tags.event_id for RSVP attribution. | Build | Survives event renames (vs slug-based tags).
Drop ~35 empty leftover tables | ~35 empty scaffolding tables (old CRM, social manager, feed, DMs). | Export copies as a receipt, then drop. | Build | Don't drop without exporting copies first.
Drop old backup tables after soak | Backup tables from recent migrations await a 2-4 week no-regression soak. | Drop dated backup_* tables after soak; confirm stability first. | Build | Only after a 2-4 week no-regression soak.
Delete dead admin member components | An old admin members tab + profile sheet are mounted nowhere (replaced by /admin/contacts). | Delete AdminMembersTab + AdminMemberProfileSheet after confirming no revival. | Build | Already mounted nowhere; confirm no revival, then delete.
MARKETING & FRONT-END · 10 items
SEO + schema markup + pre-rendering (all front pages + 4 hub landers) | Search engines currently see near-empty pages because the public site renders client-side — so the site is close to invisible in search. This wires search-readiness into every public page AND the four hub landers. | Add schema markup (Organization / LocalBusiness / Event), SEO meta + OG tags, and server/pre-rendering so crawlers see real content; wire analytics/tracking; update the privacy policy. Scope: homepage, /join (social), /business, Events, The Network/directory, blog — plus the 4 hub landers. | Build | Moved into Phase 1. Rides alongside the hub-sites build (a hub page must exist to receive schema).
Homepage hero rebuild + image optimization | Rebuild the hero and compress oversized hero images (currently 24-30MB, should be 200-800KB). | Hero rebuild + compress images. | Build | Includes compressing 24-30MB hero images to 200-800KB.
Homepage copy rewrite + slogan | Rewrite homepage body/section copy and update the slogan. | Body + section copy + slogan. | Build | Needs the copy spec.
Fix the mobile hero sliding bug | A visual bug where the hero image slides on mobile. | Mobile hero sliding fix. | Build | Fix the hero sliding on mobile.
The Exchange page | Build The Exchange page (speaker-driven business event product page). | The Exchange page. | Build | Speaker-driven business-event product page.
Sponsor page (likely folds into /business) | Sponsor functionality — likely folds into the /business application routing. | Probably absorbed by the /business rebuild. | Build | Likely folds into the /business rebuild — confirm first.
/business page rebuild with dynamic application | Rebuild /business as one page with a dynamic application routing prospects to membership, Preferred Business, or sponsorship by their answers. | Dynamic diagnose-before-offer application. | Build | Routes prospects to membership, Preferred Business, or sponsorship.
Charlotte hub landing sites (4 public landers) | Four audience-specific public landers (cltarrival / cltfounded / clteatsandevents / cltreset) that funnel Charlotte audiences into the club. | 4 public landers, shared skeleton, own design pass, fully pre-rendered + schema (see SEO item). They feed The Network. | Build | Public landers can ship earlier; they pair with The Network below.
The Network — four hubs + members rolled up | The four hubs rolled up into one view, plus all members. Two faces reading the same data: a PUBLIC face (the hub landers + business/partner listings — the sales asset) and an INTERNAL in-portal view that rolls up everyone. Social members appear ONLY on the internal in-portal view — never on the public hubs. | Roll the four hubs into one Network view + members. Public face = hubs / business + partner listings (social members excluded). Internal face = full rolled-up view including social members. Reads the same hub data as the landers. | Build | Depends on the portal + identity foundation. Social members are internal-only on The Network. Separate from the member directory (people-only).
Instagram comment auto-DM (ManyChat) | Auto-DM people who comment a keyword on Instagram posts. | ManyChat comment -> auto-DM. | Build | Copy provided internally.
AI / AGENTS (LATER EFFORT) · 2 items
AI concierge + agent platform | A conversational SMS concierge (drafts replies for human approval) + a later agent roadmap, on the texting foundation; human-approval queue mandatory. | Built on the portal texting inbox (Layer 1). Soft-launch 5 members, 80%+ approve-unedited before any auto-send. | Build | Sits on top of the texting inbox once it exists; a later effort. Matchmaker never auto-sends.
AI foundations (memory, embeddings, coordination) | Supporting infra for the agents: shared memory, member embeddings, multi-agent coordination, model routing. | pgvector + embeddings, agent_memory, multi-agent coordination, model routing. | Build | A later effort; supports the agents (embeddings, memory, routing).
EVENT DISCUSSION & NOTIFICATIONS + JUL-5/6 FINDINGS — IN-HOUSE (NOT ON THE DEVELOPER SHEET) · 12 items
Rotate the R2 media token (exposed key) | The R2 Access Key ID + Secret for bucket 704-discussion-media were exposed in a working chat (screenshot/paste). Scope = that one media bucket only — low blast radius, but rotate. | After 6c ships: Cloudflare -> R2 -> API tokens -> re-create 704-discussion-upload (Object Read & Write, bucket-scoped) -> supabase secrets set the two new values -> confirm an upload still works. | Declined | Adam declined rotation Jul 5 - standing watch item. Key scope = one media bucket only (no member data / money / DB). Say 'rotate' anytime: ~2 min.
Verify/finish the Alerts page (full history, discussion types) | Locked: bell badge clears on open, items dismiss via X, but the ALERTS PAGE keeps every notification forever - markable read (single + all). PARTIAL Jul 5: /dashboard/notifications now honors action_url (deep-links verified end to end). Remaining: full-history + mark-read behavior verification. | Read the Alerts page code; verify full-history + mark-read behavior and that all discussion notification types display with correct deep-links; fix gaps. Desktop + mobile test. | Verify | Deep-links fixed+verified Jul 5 (commit e9f6250). Remaining: verify full-history retention + mark-read (single + all).
Messaging: bells for messages in existing conversations | Messaging was resurrected Jul 5 (DMs/groups had NEVER worked since launch: RETURNING/RLS deadlock, participants-insert policy tautology, content-vs-body + title-vs-name schema mismatches, 4 missing messages columns - all fixed and verified end to end). Remaining gap: notifyNewConversation only fires on conversation CREATION, so messages into an existing thread produce no bell. | Add a new_message bell per message into an existing conversation, throttled (e.g. skip if an unread new_message bell for that conversation already exists). | Build | Follow-on to the Jul 5 messaging resurrection. Recipients currently only get notified on the first-ever message.
Messaging: attachment uploads (images/files) | MessagingView has image/file upload code paths and messages now has image_urls/file_urls/file_names columns (added Jul 5), but the storage wiring (bucket, upload flow) has never been tested and may not exist. | Audit the attachment path end to end: storage bucket, upload call, render. Fix or wire what's missing. Desktop + mobile test. | Build | Text messaging + edits verified Jul 5; attachments explicitly skipped in that test.
Fix the business_hubs 404 on dashboard | The dashboard queries a business_hubs table that doesn't exist (PGRST205 404 on every load; hint suggests business_cards). Pre-existing; harmless but noisy in every console. | Find the business_hubs query, point it at the right table or remove the dead widget. | Build | Appears on every dashboard load for all roles. Low risk, quick fix.
Review the 3 Security Definer view advisor flags | Supabase Advisor flags member_counts, active_members, and event_participants_view as SECURITY DEFINER views. member_counts is deliberate (the locked member-count source); the other two need review. | Review active_members + event_participants_view: confirm intended or convert. Do during the identity-foundation phase. | Build | member_counts stays as-is (locked). Fold into identity/cleanup work.
Verify the first real-money admin refund (Remove & Refund) | Admin Remove & Refund shipped Jul 5 (edge fn admin-refund-ticket: admin gate, Stripe refund, void credential, seat freed; + attendee-dialog button, mobile-safe). Every branch proven EXCEPT the successful real-money refund line: void-only path, 403 gate, already-voided idempotency, and the Stripe-failure 502 fail-safe (no seat freed without money returned) all tested live. | WAIT mode: on the next genuine member refund request, use Remove & Refund in the event attendee dialog and verify: Stripe refunded, credential voided, seat freed, toast correct. | Verify | Zero-cost proof on the next real request. Sacred Walker (Jul 5) handled manually pre-feature; her case is the template.
Nine-job cron auth resurrection (root cause: wrong Vault key format + SQL typo) | The Jul-5 sheet knew of 2 dead crons; a full audit Jul 7 found NINE broken. Two classes: (a) 5 jobs 401'd because functions do a strict token===SERVICE_ROLE_KEY check and Vault held the legacy JWT, but the Edge runtime injects the NEW sb_secret_ key - dashboard key != runtime key; (b) 3 jobs (process-drips, renewal-reminders, re-engagement) crashed on a SQL typo 'value' vs 'decrypted_secret' before any HTTP call. Plus event-reminder had NO service-key path at all. | DONE Jul 7: Vault SUPABASE_SERVICE_ROLE_KEY updated to the sb_secret_ runtime key (fixes jobs 11/12 with no code) + cron.alter_job regex-fixed the 'value'->'decrypted_secret' typo on jobs 3/4/13. All 7 revived jobs confirmed 200 on live ticks. process-drips sent 5 real drips clean. | Verify | Superseded the 2 old cron rows. sb_secret_ key + legacy JWT both appeared in chat -> on the rotation burn list. Jobs 2/10 intentionally left disabled pending guards (next rows).
event-reminder: require auth, accept service key, close no-header mass-email hole | SECURITY: event-reminder only ran auth 'if (authHeader)' - a POST with NO Authorization header skipped auth and proceeded to email ~99 members. Also had no service-role path so cron always 401'd. | DONE Jul 7 (commit 09d637d): auth now runs unconditionally; missing token -> 401; token===SERVICE_ROLE_KEY -> authorized (cron path); else getUser + existing admin-role gate. Deployed + probed: no-header=401, sb_secret_=200 no-op. Passes cron at 11:00 UTC. | Verify | Two-layer now (platform JWT gate + in-function). First big by-design send is Jul 11 SupperClub day (~180).
Guard business-profile-reminder before re-enabling (job 2) | business-profile-incomplete-reminder has NO send-history dedupe - once revived it nags all 19 incomplete business profiles every 2 days forever. Disabled Jul 7 before the Vault swap so the fix wouldn't wake it. | Add a per-member cooldown (e.g. max one nag / 14 days) using a log row or contact_activity, THEN cron.alter_job active:=true. Read the function first. | Build | Job currently active=false. One of two guards gating re-enable.
Guard guest-event-match before re-enabling (job 10) | guest-event-match-daily first successful run would email up to 69 guests about events touched in the last 7 days - including SupperClub, which is at capacity (would pitch a sold-out event). Disabled Jul 7 before the Vault swap. | Add an at-capacity exclusion (skip events with no seats left) to the eligible-events query, THEN re-enable. Dedupe table guest_event_notifications already exists. Read the function first. | Build | Job currently active=false. Second of two guards gating re-enable.
Fix ambassador-payout week_label insert (non-existent column) | ambassador-payout inserts a week_label column into ambassador_payouts that doesn't exist (real cols: amount_cents, stripe_transfer_id, status...). Every payout-log insert would fail - Stripe transfers with NO row in the payout log. Non-fatal today (payout queue empty; 0 rows ever) but must fix before any real ambassador payout. | Read ambassador-payout; remove week_label from the insert (or add the column to the table). Confirm an insert succeeds on a dry payout. | Build | Found during the Jul 7 cron audit. Pairs with the ambassador referral/payout rows above. Job 8 itself is safe Monday (empty queue, lenient auth).
PHASE 2 · MAJOR BUILDS (each gets its own detailed scope before build)
MAJOR BUILDS — EACH GETS ITS OWN DETAILED SCOPE BEFORE BUILD · 7 items
CRM system | Full customer-relationship system built ON the merged person record: 360-degree member view, segments/audiences, lifecycle tracking. The internal data model IS the CRM (not a re-introduced external tool). | Own detailed scope before build. | Phase 2 | Built on the canonical person record from Phase 1. Currently hidden behind the reversible HIDE_CRM_AND_PARTNERS middleware flag (carve-out keeps /admin/crm/campaigns live for the newsletter).
Preferred Business Network | New paid product: vetted local-business listings, $300/mo to be listed. Lives in the portal first, public domains later. Includes the internal 'Seats' system. Social members browse this to find services. | Own detailed scope before build. | Phase 2 | Plugs into The Network surface built in Phase 1.
Partner Portal (audit, then repurpose or remove) | An existing, mostly-built partner portal of unclear purpose. Audit it, then either repurpose it as the Preferred Business Network management surface or remove it. Frozen until then. | Own detailed scope before build. | Phase 2 | Audit first; likely becomes the Preferred Business Network management surface. Currently hidden behind the reversible HIDE_CRM_AND_PARTNERS middleware flag.
Task center for admins (lite project tool) | A super-light ClickUp-style task center for admins/super-admins: create, assign, track tasks. | Own detailed scope before build. | Phase 2 | Lite task assignment + tracking for admin / super-admin.
Shared email inbox view for super-admins | A shared inbox view so super-admins can see the team email (hello@) in one place. | Own detailed scope before build. | Phase 2 | Super-admin visibility into hello@.
Corporate / bulk-sales floating-seats portal | A portal for selling memberships in bulk to companies, with reassignable 'floating' seats. | Own detailed scope before build. | Phase 2 | Reassignable floating seats for companies.
Full mobile app | A full native mobile application. The largest Phase 2 build. | Own detailed scope before build. | Phase 2 | The final, largest Phase 2 effort.